## Executive Dashboard
GB IT COMMUNITY PAVILION — EXECUTIVE DASHBOARD
"Made in GB" · 28th ITCN Asia · 22–24 Sep 2026 · Expo Centre Karachi · setup 19–21 Sep · dismantle 25 Sep · Year 2: 29th ITCN Asia, Lahore 29–31 Jan 2027. Strategic funnel: Visibility → Connections → Leads → Partnerships → MOUs → Business → Economic Impact.
MISSION
Use the free three-year GB Pavilion (Assumption A1 — confirm in writing by 5 Sep) as a strategic platform: position Gilgit-Baltistan as a credible technology ecosystem and convert visibility into measurable business for ~10 GB companies — leads, clients, investors, federal & international connections, MOUs, exports. Each ITCN must be stronger than the last.
KEY DATES
Kickoff & governance | 3–4 Sep |  | ECG written confirmation (A1/A2) | by 5 Sep
Budget with real quotes ratified | 6 Sep |  | Applications close / selection | 7 Sep / 8 Sep
Assets & sponsor logos freeze → print files out | 12 Sep |  | Travel & hotel booked | by 11 Sep
A-list VIP invitations dispatched | 14 Sep |  | Print proofs approved | 15 Sep
Rehearsals ×2 / Go-No-Go review | 15–16 / 17 Sep |  | Main travel wave (weather fallback armed) | 18 Sep
Setup complete & signed off | 21 Sep 18:00 |  | SHOW DAYS | 22–24 Sep
Dismantle · leads 100% assigned | 25 Sep |  | 30 / 60 / 90-day reviews | 24 Oct · 23 Nov · 23 Dec
Year-2 decision + ECG booking (Lahore) | by 30 Nov
KPI SNAPSHOT (live — targets are recommendations, ratify at kickoff)
Metric | Target | Actual (live) | Source sheet | Reading
Companies confirmed | 10 | 0 | Participating Companies | Roster locked 9 Sep
Sponsorship committed (PKR) | cover ≥60% of budget | 0 | Sponsors & Funding | Letters on file only
Budget requirement (PKR) | quotes by 6 Sep | 5120500 | Budget Tracker | Placeholders until quoted
Funding coverage % | ≥60% | 0 | Budget Tracker
B2B meetings held | ≥40 | 0 | B2B Meetings | ≥40 booked pre-show
Leads captured | ≥150 | 0 | Lead Tracker | L-IDs only
Qualified leads (Hot+Warm) | ≥50 | 0 | Lead Tracker
VIP visits hosted | ≥8 | 0 | Gov-VIP Engagement | Every visit → an ask
MOUs signed | ≥5 | 0 | MOU Tracker | Signings ≠ success…
MOUs converting (Proposal+) | ≥2 by day 60 | 0 | MOU Tracker | …conversion is
Pipeline value (PKR) | quantified by day 60 | 0 | Lead Tracker
Social posts published | ≥40 | 0 | Social & PR Calendar
Open risks | trend ↓ | 22 | Risk Register | Score 6+ = in motion
PHASE STATUS (update at standup)
Phase | Window | Owner | Status | Note
P1 Strategy & Governance | 3–5 Sep | Project Director | Not started
P2 Company Mobilization | 3–12 Sep | Companies Lead | Not started
P3 Funding & Sponsorship | 4–19 Sep | Sponsorship Lead | Not started
P4 Pavilion Design & Branding | 8–21 Sep | Design Lead | Not started
P5 Stakeholder Engagement | 8–24 Sep | Stakeholder Lead | Not started
P6 BD & B2B Meetings | 9–24 Sep | BD Lead | Not started
P7 MOU & Partnerships | 10 Sep–23 Dec | PD + PMO | Not started
P8 Social, PR & Media | 5 Sep–15 Oct | Comms Lead | Not started
P9 Logistics | 5–27 Sep | Logistics Lead | Not started
P10 ITCN Execution | 19–25 Sep | Project Director | Not started
P11 Post-Event Follow-Up | 25 Sep–23 Dec | PMO / Follow-up | Not started
TOP RISKS THIS WEEK (full register: Risk & Issue Register)
R1 weather vs 18–19 Sep flights (fallback armed by 11 Sep) · R2 pavilion terms not yet in writing (escalate 5 Sep) · R5 funding gap (wave-1 asks 7 Sep) · R6 Karachi print slip (proofs 15 Sep hard gate) · R10 post-event follow-up decay (owners assigned before leaving Karachi).
COMMAND & CONTACTS (fill 3–4 Sep)
Project Director |  |  | phone / email
PMO / Follow-up Lead |  |  | phone / email
PASHA/ECG Liaison |  |  | phone / email
BD & B2B Lead |  |  | phone / email
Logistics & Travel Lead |  |  | phone / email
Comms & Media Lead |  |  | phone / email
THIS WEEK FOCUS (PD writes 3 lines every Monday)

## README
GB IT COMMUNITY PAVILION @ ITCN ASIA — MASTER PROJECT WORKBOOK
Single source of truth for the "Made in GB" Pavilion, 28th ITCN Asia, 22–24 Sep 2026, Expo Centre Karachi. Prepared 3 Sep 2026.
HOW TO USE THIS WORKBOOK
Owner | The Project Director owns this workbook. One person (PMO/Follow-up Lead) maintains it daily; nobody else edits structure.
Update cadence | Sep 3–21: update daily by 18:00 before the standup. Show days: update at the 18:30 debrief. Post-event: weekly, then at the 30/60/90-day reviews.
Start here | Executive Dashboard (status at a glance) → Daily Action Plan (what to do today) → Master Timeline (the full plan). Everything else is a working register for one workstream.
Activity logic | Every major activity carries WHAT → WHY → WHO → WHEN → HOW → DEPENDENCY → OUTPUT → KPI. If an activity has no owner and no deadline, it does not exist.
Status values | Use the dropdowns: Not started / In progress / Done / Blocked / At risk. "Blocked" requires naming the blocker in the Risk & Issue Register.
Dates | All dates are 2026 unless marked. Event anchor: setup 19–21 Sep, show 22–24 Sep, dismantle 25 Sep (Expo Centre Karachi).
Facts vs assumptions | The "Facts & Assumptions" sheet separates verified research (with sources) from working assumptions. Resolve every assumption by its due date — several are blocking.
Money | All amounts in PKR. Budget figures are PLACEHOLDER ESTIMATES to be replaced with real quotes by 6 Sep — the structure is what matters.
COLOUR LEGEND
Dark green header | Table headers — do not edit
Pale green band | Section labels
Amber cell | Decision or input the team must provide
Grey cell | Formula — do not type over it
Grey italic row | Example row showing expected format — replace with real data
SHEET MAP
Sheet | What it is for
Executive Dashboard | Status at a glance: key dates, KPI actuals vs targets (live formulas), phase status, top risks, command contacts.
Facts & Assumptions | Verified research findings with sources vs. working assumptions with owners and resolve-by dates.
Master Timeline | The full 11-phase plan, Sep 3 → Dec 23 (+ year-2 kickoff): every activity with WHY/WHO/WHEN/HOW/dependency/output/KPI.
Daily Action Plan Sep 3-18 | The 16-day sprint, day by day, with owners and outputs. This drives the daily standup.
Weekly Targets | Week-by-week targets from kickoff through the 90-day review.
Committee & Governance | Roles, names, responsibilities, decision matrix, meeting cadence, communication channels.
Participating Companies | Selection rubric, application process, and the 10+2 company roster with per-company readiness checklist.
Sponsors & Funding | P3.2 — value proposition, sponsor categories with evidence-based hooks, tier benefits matrix (the negotiation boundary), revenue plan with live honesty math.
Sponsor Pipeline | P3.3 — target database + 8-stage sales pipeline in one tracker: hooks, warm paths, probability-weighted values, live funnel and weekly targets.
Sponsorship Daily Plan | P3.3 — sponsorship track day by day, 3–18 Sep: priorities, owners, expected outcomes, deadlines, dependencies, KPIs.
Stakeholder Database | Everyone who should know about or visit the pavilion, by category and priority, with invitation status.
Government-VIP Engagement | VIP-by-VIP objectives, asks, channels, visit slots, protocol checklist.
Pavilion Design & Branding | Pavilion concept, zone plan for ~90 m², production checklist with deadlines, what-ECG-provides checklist.
Logistics | Delegate manifest, travel waves (with weather fallback), hotel, equipment, documents, emergency contacts.
B2B Meetings | Target-list process, meeting calendar for 3 show days, and the meeting log that feeds the Lead Tracker.
MOU & Partnership Tracker | MOU pipeline from identification to signing to conversion (meeting → opportunity → proposal → contract → revenue).
Social Media & PR Calendar | Dated content plan before/during/after, plus press targets and media kit checklist.
Risk & Issue Register | Scored risks with mitigations, contingencies, owners. Review at every standup.
Budget Tracker | P3.1 — funding requirement matrix: three budget scenarios (minimum viable / recommended / enhanced), mandatory vs optional, funding route per line (must-fund / sponsorable / in-kind / cost-share / negotiated free), live funding summary.
Lead Tracker | Every visitor captured: qualification, owner, follow-up date, outcome stage. The single most important post-event asset.
30-60-90 Follow-Up | The post-ITCN conversion machine: 48h/7d/30d/60d/90d actions, owners, metrics.
KPIs & Impact Measurement | KPI definitions, baselines, targets, live actuals, source-of-truth sheet per KPI.
Post-Event Report
Strategic principle: the pavilion is a three-year platform, not a one-off booth cluster. Design every action around the funnel Visibility → Connections → Leads → Partnerships → MOUs → Business → Economic Impact, and make each ITCN stronger than the last (next stop after Karachi: 29th ITCN Asia, 29–31 Jan 2027, Expo Centre Lahore).

## Facts & Assumptions
VERIFIED FACTS vs WORKING ASSUMPTIONS
Verified = supported by a public source found in research on 3 Sep 2026 (source cited). Assumption = working basis chosen by the planning team — resolve by the date shown. Do not treat assumptions as facts.
A. VERIFIED FACTS (from research, 3 Sep 2026)
# | Fact | Detail | Source | So what / action
1 | Event dates & venue | 28th ITCN Asia: 22–24 Sep 2026, Expo Centre Karachi. Setup 19–21 Sep, dismantling 25 Sep. Show hours 10:00–18:00. | itcnasia.com/karachi; TDAP Expo Centre Karachi booking schedule (Apr 2026); 2025 visitor guide | Anchor the whole plan; delegation must be in Karachi by 20 Sep evening.
2 | Next edition (year 2) | 29th ITCN Asia announced: 29–31 Jan 2027, Expo Centre Lahore. Co-located: Global CISO Summit, Web3 & Blockchain Forum, Fintech Forward. | itcnasia.com/home | Year-2 of the 3-year commitment is only ~4 months after Karachi — decide participation at the 60-day review (23 Nov).
3 | Organizer & contacts | E-commerce Gateway Pakistan (ECG). info@itcnasia.com, +92-21-38709970. Official freight agent: APT Showfreight (Iqureshi@aptshowfreight.com, +92 21 32411158-9). | itcnasia.com; TDAP booking schedule | Use for written confirmation of pavilion terms, exhibitor manual, passes.
4 | "Made in GB" pavilion announced | P@SHA Senior Vice Chairman Muhammad Umair Nizam publicly announced a dedicated 'Made in GB' pavilion to showcase GB companies at ITCN Asia (Nov 2025), alongside P@SHA's first GB CXO Meetup (with GBSHA) and plans for a P@SHA GB office. | ProPakistani, 19 Nov 2025 | Use "Made in GB" as the pavilion identity — it already exists in the public narrative.
5 | Key person dual role | Muhammad Umair Nizam is simultaneously P@SHA Senior Vice Chairman and VP/Group Director of ECG (ITCN organizer) — the credible channel for the pavilion commitment. | Business Recorder Sep 2025; P@SHA CEC page; ITCN visitor guide | Route pavilion confirmation through his office; copy P@SHA secretariat and ECG.
6 | P@SHA leadership context | P@SHA Chairman Sajjad Mustafa Syed was reinstated by the Directorate General of Trade Organisations on 28 Aug 2026 after a contested no-confidence vote (Umair Nizam briefly acting chairman). | TechJuice, Aug 2026 | Keep engagement institutional: write to both the P@SHA secretariat and ECG; get all pavilion terms in writing regardless of association politics.
7 | GB IT sector baseline | P@SHA's first 'GB IT & ITES Sector Diagnostic Report' (Nov 2025): ~300 SECP-registered firms, 100–120 active (~$3.5M revenue); 3,000–4,000 freelancers earning $10–15M/yr; sector total $15–18M; workforce 6,000–7,000; 68% of firms in Gilgit district; 88% report power-outage disruption. Report recommends subsidised access to tech expos. | ProPakistani 19 Nov 2025; Business Recorder 20 Nov 2025; pasha.org.pk publications | Use stats on the ecosystem wall and in the sponsor deck; use the subsidy recommendation as the hook for PSEB/GB-govt funding asks.
8 | GBSHA exists | Gilgit Baltistan Software Houses Association: 40+ member companies, 2,000+ IT professionals (self-reported). Co-hosted the GB CXO Meetup with P@SHA. | gbsha.org.pk | Primary mobilization channel for the call-for-applications.
9 | Federal names (verify at invite time) | IT Minister Shaza Fatima Khawaja; MoITT Secretary Zarrar Hasham Khan (moitt.gov.pk, 3 Sep 2026); PSEB CEO Faisal Jeddy (appointed Jan 2026); Ignite CEO Muhammad Bilal Abbasi (appointed Jun 2026). | moitt.gov.pk; ProPakistani Jan & Jun 2026 | Stakeholder Database rows prefilled; re-verify each officeholder before dispatching invitations.
10 | GB government (verify portfolios) | CM Amjad Hussain (Azar) elected 22 Jun 2026; 12-member cabinet notified 22 Jul 2026 (IT portfolio holder not named in sources). GB Secretary IT: Zameer Abbas (gbit.gov.pk, 3 Sep 2026). | Pamir Times/Tribune Jun 2026; Aaj Jul 2026; gbit.gov.pk | Confirm the elected IT minister via Secretary IT before invitations.
11 | Pavilion precedents | ITCN editions have hosted STZA (with SIFC support), PSEB, Ignite, State Bank/Capital Market pavilions; 2024 edition reportedly generated $500M in MoUs; Sep 2025 Karachi edition drew 67,000+ attendees. 28th edition organizer claims: 850+ booths, 75,000+ trade visitors, 350+ international delegates (organizer-claimed). | Radio Pakistan Jan 2026; Business Recorder Sep 2025; Express Tribune Sep 2025; itcnasia.com | Group pavilions are normal practice — ask ECG for the same services STZA/PSEB pavilions receive.
12 | Booth module norm | ECG's booking form sells space in 9 m² modules (9–90 m²). | itcnasia.com/karachi/book-now | A 10-company pavilion ≈ 90 m² (10 modules) — matches the "90 × 90" space described.
13 | Travel reality | Gilgit–Islamabad: PIA only, 3× weekly (Fri/Sat/Sun, 48-seat ATR, ~1h15m), frequent weather cancellations; NATCO road option ~18h+. Skardu has more reliable jet service (incl. Airblue A320). Karachi requires connection via Islamabad. | flightsfrom.com (Sep 2026 schedule); Wikivoyage; Chitral Today | Travel plan needs hard buffers + road fallback; see Logistics sheet.
14 | TDAP & partners | TDAP administers Expo Centre Karachi bookings and partners ITCN; NITB and P@SHA listed as partners. TDAP precedent: 36 Pakistani firms at GITEX Global 2025. | TDAP booking schedule; itcnasia.com; ProPakistani Oct 2025 | TDAP is a channel to international delegations and future export platforms (GITEX).
15 | GB tech infrastructure | SCO Software Technology Parks in Gilgit & Skardu (2020) and Nasirabad Hunza with AKF (Jun 2024); SCO–KIU incubation centre (2021); SCO freelancing hub Tallu, Skardu (Feb 2025). GB IT Dept runs Google Career Certificates (1,000 trained), e-Rozgaar + 5% loans via Karakoram Cooperative Bank, UNDP e-governance partnership. | sco.gov.pk; AKDN Jun 2024; Samaa Feb 2025; gbit.gov.pk | SCO, AKF/AKDN, UNDP, KCBL = natural sponsors/partners with GB-tech precedent; STP startups = candidate companies.
16 | Macro narrative | Pakistan IT exports hit a record $4.6B in FY2025-26. GB freelancers out-earn GB formal firms ~4–5×. | ProPakistani Jul 2026; P@SHA diagnostic | Pavilion story should include the freelance economy, not only software houses.
17 | 2025 Lahore edition postponed | The May 2025 ITCN Asia Lahore edition was postponed (regional tensions) and held 17–20 Jan 2026 in Lahore; the only 2025 edition was Karachi, 23–25 Sep 2025. Media edition-numbering is inconsistent. | startup.pk; Pakistan Consulate LA; Radio Pakistan Jan 2026 | See assumption A3 on mapping the first GB delegation to the right edition.
B. WORKING ASSUMPTIONS & OPEN DECISIONS (resolve by due date — amber = blocking)
ID | Assumption / open item | Working basis | Owner | Resolve by / how
A1 | Free pavilion + three-year commitment | Committed verbally by P@SHA SVC / ECG per the community; NOT found in any public record. Treated as real but undocumented. | PASHA/ECG Liaison | BLOCKING — written confirmation from ECG by 5 Sep: space, location, inclusions, passes, 3-year frame (incl. Lahore Jan 2027).
A2 | "90 × 90" space | Interpreted as ≈90 m² (10 × 9 m² modules), consistent with ECG booking units. Could also mean 90 sq ft/m dimensions. | Design Lead | BLOCKING — exact dimensions, orientation, open sides, ceiling height from ECG exhibitor manual by 8 Sep.
A3 | First GB delegation edition | Community describes 'ITCN Asia Lahore 2025'; public record shows that edition happened 17–20 Jan 2026. Delegation history mapped to Jan 2026 Lahore (or Sep 2025 Karachi). | Project Director | Confirm internally by 6 Sep; adjust the narrative/baseline in KPIs sheet accordingly.
A4 | Delegation size = 25 | 10 companies × 2 reps + ~5 core team (PD, PMO, Comms, Logistics, Design/floater). | Project Director | Ratify at kickoff 3–4 Sep; drives budget, travel, hotel, passes.
A5 | Budget figures | All amounts in Budget Tracker are placeholder estimates (Sep 2026 price levels) pending quotes. | Sponsorship & Finance Lead | Replace with real quotes by 6 Sep (travel, hotel, print, AV, van).
A6 | Cost-share policy | Default: sponsorship covers shared costs (pavilion branding, common infra, media); companies cover own travel/hotel unless sponsorship closes the gap. | Steering Committee | Decide 5–6 Sep BEFORE companies commit, and state it in the call-for-applications.
A7 | Exhibitor passes count | Assume 2 per company + core team; actual allocation unknown. | Logistics Lead | Confirm with ECG by 8 Sep; passes data submitted by 12 Sep.
A8 | Shell-scheme inclusions | Assume fascia, basic walls, carpet, 1 power point, 2 chairs+table per module; everything else self-produced/rented. | Design + Logistics | Confirm from exhibitor manual by 8 Sep; order extras via ECG contractor by 15 Sep.
A9 | KPI targets | All 2026 targets in KPIs sheet are recommendations calibrated to a first Karachi outing. | Steering Committee | Ratify at kickoff (3–4 Sep); do not change after 8 Sep.
A10 | Sponsorship tier pricing | Title 1.5M / Gold 750k / Silver 300k PKR + in-kind — recommended, based on delegation budget scale. | Sponsorship Lead | Ratify 5 Sep with the budget.
A11 | Officeholder names | Ministers/CEOs verified as of the source dates shown in Facts; roles change. | Stakeholder Lead | Re-verify every name before its invitation goes out (10–11 Sep).
A12 | Connectivity | SCOM SIMs may not serve well outside GB; assume delegates need Jazz/Zong SIMs + 2 hotspot devices for the booth. | Logistics Lead | Confirm venue internet options with ECG by 15 Sep; buy SIMs on arrival 20 Sep.
A13 | Sponsorship economics are planning assumptions | Tier prices (Title 1.5M / Gold 750k / Silver 300k / Supporting 100k), target mix (cash 1.85M + in-kind 1.2M ≈ 60% of budget), and pipeline probability weights are planning tools, not market-tested rates or commitments. | Sponsorship Lead | Ratify tiers 4–5 Sep; recalibrate probabilities at the 12 & 15 Sep pipeline reviews.
Research method: web research on 3 Sep 2026 across itcnasia.com, pasha.org.pk, gbit.gov.pk, sco.gov.pk, TDAP, ProPakistani, TechJuice, Business Recorder, Dawn, Radio Pakistan, Pamir Times, AKDN and others. LinkedIn/Facebook content was largely not indexable — much GB community activity lives there, so absence from this sheet is not evidence an event did not happen. No public record was found of: the free/3-year pavilion terms, the first GB delegation coverage, or a specific Tech AlphaLogix CXO/COE event (the Coalition of Employers mechanism in GB/Chitral is documented under the AKFC BEST4WEER program).

## Master Timeline
MASTER TIMELINE — 11 PHASES, 3 SEP → 23 DEC 2026 (+ YEAR-2 KICKOFF)
Every activity: WHAT (activity) → WHY → WHO (owner) → WHEN (start/deadline) → HOW → DEPENDENCY → OUTPUT → KPI. Owners are roles from Committee & Governance. Priority: P1 = must happen on time or the pavilion fails; P2 = important; P3 = valuable. Update Status daily.
Phase | ID | Activity (WHAT) | WHY | Prio | Start | Deadline | Owner (WHO) | HOW (method) | Dependency | Output | Success metric / KPI | Status | Risks / blockers
P1 Strategy & Governance | 1.1 | Kickoff: ratify objectives, KPI targets, cost-share policy, delegation size | Alignment before speed — every later decision tests against these | P1 | 2026-09-03 | 2026-09-04 | Project Director | 90-min kickoff meeting; adopt KPIs sheet targets & assumptions A4/A6/A9 | — | Signed-off objectives memo in shared drive | Objectives + KPI targets ratified by 4 Sep | Not started | Committee availability at short notice
P1 Strategy & Governance | 1.2 | Obtain WRITTEN confirmation of pavilion terms from ECG/P@SHA | Free space & 3-yr commitment exist only verbally (Assumption A1); everything downstream depends on exact terms | P1 | 2026-09-03 | 2026-09-05 | PASHA/ECG Liaison | Letter/email to Umair Nizam office + info@itcnasia.com: space, location on floor, inclusions, passes, setup access, deadlines, 3-yr frame; request exhibitor manual | — | Confirmation letter + exhibitor manual on file | Terms documented by 5 Sep | Not started | Politeness delay — escalate via PD phone call 5 Sep if silent
P1 Strategy & Governance | 1.3 | Form Pavilion Committee; fill every role | One accountable owner per workstream or the sprint stalls | P1 | 2026-09-03 | 2026-09-04 | Project Director | Fill Committee & Governance sheet; confirm daily availability Sep 3–25 | 1.1 | Committee sheet complete with names & numbers | All 11 roles filled by 4 Sep | Not started | Volunteer overload — cap roles at 2/person
P1 Strategy & Governance | 1.4 | Adopt decision & approval matrix + escalation path | 15-day sprint cannot wait on consensus for every choice | P1 | 2026-09-03 | 2026-09-05 | Project Director | Ratify matrix in Committee sheet (who signs off budget, selection, design, press, VIP asks) | 1.3 | Approval matrix adopted | Zero decisions >24h stuck (tracked at standup) | Not started
P1 Strategy & Governance | 1.5 | Open channels: committee WhatsApp, companies WhatsApp, shared drive, workbook owner | Single source of truth from day one | P1 | 2026-09-03 | 2026-09-04 | PMO / Follow-up Lead | This workbook = master; drive for assets; groups for speed; PMO updates workbook 18:00 daily | 1.3 | Channels live, all members joined | 100% committee in channels by 4 Sep | Not started
P1 Strategy & Governance | 1.6 | Set cadence: daily 30-min standup 18:00 (Sep 3–21), show-day debrief 18:30, weekly steering | Rhythm beats heroics | P1 | 2026-09-03 | 2026-09-04 | Project Director | Calendar invites; standing agenda: yesterday/today/blockers/risks | 1.3 | Recurring invites accepted | ≥90% standup attendance | Not started
P1 Strategy & Governance | 1.7 | Adopt participating-company criteria & approval process | Transparent, defensible selection protects community trust | P1 | 2026-09-03 | 2026-09-04 | Companies Lead | Ratify rubric on Participating Companies sheet; GBSHA co-signs; conflict-of-interest rule (scorers abstain on own company) | 1.3 | Published criteria + application form | Criteria public before applications open | Not started | Perceived favouritism — publish rubric with the call
P1 Strategy & Governance | 1.8 | Frame year-2/year-3 with P@SHA/ECG in the same confirmation | A 3-year platform must be negotiated as one, not re-begged yearly | P2 | 2026-09-04 | 2026-09-12 | PASHA/ECG Liaison | Include Lahore 29–31 Jan 2027 + 2027/28 edition in the written confirmation (1.2) | 1.2 | 3-year frame referenced in writing | Year-2 named in the confirmation letter | Not started
P2 Company Mobilization | 2.1 | Launch call for applications across GB IT community | Reach all ~120 active companies + STP/incubator startups fast | P1 | 2026-09-04 | 2026-09-05 | Companies Lead + GBSHA | Application form (rubric fields); push via GBSHA (40+ members), SCO STPs Gilgit/Skardu/Hunza, KIU incubator, WhatsApp groups, social announcement | 1.7 | Applications open with 7 Sep deadline | ≥25 applications by 7 Sep | Not started | Short window — pair with direct calls to strong candidates
P2 Company Mobilization | 2.2 | Community info session (online, evening) | Set expectations honestly: costs, commitment, what the pavilion is and is not | P1 | 2026-09-06 | 2026-09-06 | Companies Lead | 1-hr Zoom: opportunity, criteria, cost-share policy (A6), obligations (2 reps, assets, rehearsals, follow-up SLA) | 2.1 | Session held + recording shared | ≥40 attendees | Not started | Low turnout — record & recirculate
P2 Company Mobilization | 2.3 | Close applications; panel scores against rubric | Merit + ecosystem mix, done fast | P1 | 2026-09-07 | 2026-09-08 | Selection Panel | Score 100-pt rubric; aim for sector diversity + Gilgit/Skardu/Hunza spread + women-led inclusion | 2.1 | Score sheet archived | All applications scored by 8 Sep 12:00 | Not started | Ties — PD casting vote
P2 Company Mobilization | 2.4 | Select 10 + 2 reserves; notify; sign commitment forms | Lock the roster; reserves protect against drop-outs | P1 | 2026-09-08 | 2026-09-09 | Companies Lead | Commitment form: 2 named reps, CNIC data, travel needs, cost-share acceptance, asset deadlines, follow-up SLA | 2.3 | 10 confirmed + 2 reserves on roster | 10 commitment forms signed by 9 Sep | Not started | Drop-outs — activate reserves within 24h
P2 Company Mobilization | 2.5 | Collect company assets: vector logo, 150-word profile, 1-pager, product shots, demo plan | Feeds design, booklet, comms, QR profiles | P1 | 2026-09-09 | 2026-09-12 | Companies Lead | Asset checklist per company (roster columns); chase daily at standup | 2.4 | Complete asset folder ×10 | 100% assets by 12 Sep (design freeze) | Not started | Late assets = company ships with template-only pod
P2 Company Mobilization | 2.6 | Companies nominate 2 trained reps; collect pass data | Booth must never be unmanned; reps are the product | P1 | 2026-09-09 | 2026-09-11 | Companies Lead | Rep names + CNIC to Logistics for passes (9.1) | 2.4 | Rep list ×20 to Logistics | Pass data submitted 12 Sep | Not started
P2 Company Mobilization | 2.7 | Exhibition-needs survey per company (power, screen, table config, demo gear) | Order infrastructure once, correctly | P1 | 2026-09-09 | 2026-09-11 | Companies Lead → Logistics | Survey in roster columns; consolidate to ECG contractor order (4.9) | 2.4 | Consolidated needs list | Order placed 15 Sep | Not started
P2 Company Mobilization | 2.8 | Pitch & booth rehearsals ×2 + basic media training | First impressions decide whether traffic becomes leads | P1 | 2026-09-15 | 2026-09-16 | BD Lead + Comms Lead | Each company: 3-min pitch + 60-sec elevator + demo dry-run; feedback panel; media do/don't brief | 2.5 | Rehearsal scorecards; improved pitches | 10/10 companies rehearsed twice by 16 Sep | Not started | Remote rehearsal for Skardu/Hunza firms via video
P2 Company Mobilization | 2.9 | Brief companies on show operating system: lead capture, meeting etiquette, daily cadence, dress code | Consistent professional operation under one brand | P1 | 2026-09-16 | 2026-09-17 | BD Lead | 1-hr briefing + 2-page playbook; test QR lead flow live | 4.7 | Playbook acknowledged ×10 | 100% reps pass lead-capture test 17 Sep | Not started
P3 Funding & Sponsorship | 3.1 | Build full cost model with real quotes | "Free pavilion" ≠ free participation; know the true gap | P1 | 2026-09-04 | 2026-09-06 | Sponsorship Lead + Logistics | Quotes: PIA/NATCO, ISB–KHI fares, hotel block, Karachi print, AV rental, van; fill Budget Tracker | 1.1 | Budget v1 (quotes, not placeholders) | Budget ratified 6 Sep | Not started | Placeholder numbers surviving past 6 Sep
P3 Funding & Sponsorship | 3.2 | Ratify funding principle & cost-share policy (A6) | No ambiguity about who pays what before companies commit | P1 | 2026-09-05 | 2026-09-06 | Steering Committee | Decide: sponsor-covered common costs; company travel self-funded unless gap closes; hardship support rule | 3.1 | Policy stated in call-for-applications | Policy published before 2.4 commitments | Not started
P3 Funding & Sponsorship | 3.3 | Build sponsorship packages + 2-page deck | A sellable proposition, not a donation ask | P1 | 2026-09-05 | 2026-09-07 | Sponsorship Lead | Tiers on Sponsors sheet (Title/Gold/Silver/in-kind) with concrete benefits; deck reuses P@SHA diagnostic stats | 3.1 | Deck PDF + tier sheet | Deck out with first ask 7 Sep | Not started
P3 Funding & Sponsorship | 3.4 | Wave-1 asks: GB IT Dept, PSEB, SCO, AKF/Accelerate Prosperity | Mission-aligned funders with GB precedent; P@SHA diagnostic itself recommends subsidised expo access — cite it | P1 | 2026-09-07 | 2026-09-12 | Sponsorship Lead + PD | Letters + calls via P@SHA intro; specific asks (cash tier or named in-kind) | 3.3 | 4 asks delivered, meetings held | ≥2 wave-1 commitments by 12 Sep | Not started | Govt process speed — ask for letter-of-intent first
P3 Funding & Sponsorship | 3.5 | Wave-2 asks: Zong, PTCL/Ufone, Jazz, KCBL, HBL/BOP, UNDP, Ignite, TDAP | Commercial + development money widens the base | P2 | 2026-09-09 | 2026-09-15 | Sponsorship Lead | Tailored hooks (Zong = largest GB 4G expansion; KCBL = e-Rozgaar partner; TDAP = export mandate) | 3.3 | 8 asks delivered | ≥1 wave-2 commitment by 15 Sep | Not started
P3 Funding & Sponsorship | 3.6 | In-kind asks: PIA fares, Karachi hotel, print discount, ECG extras (passes/branding spots) | Every in-kind rupee shrinks the cash gap | P2 | 2026-09-08 | 2026-09-15 | Sponsorship + Logistics | Barter visibility (logo on pavilion, thank-you posts, report credit) | 3.3 | In-kind letters | ≥PKR 500k equivalent in-kind | Not started
P3 Funding & Sponsorship | 3.7 | Close & document commitments; benefits-fulfillment plan | Deliver what was sold or lose year-2 sponsors | P1 | 2026-09-15 | 2026-09-19 | Sponsorship Lead | MoU/letter per sponsor; fulfillment checklist (logos to design by 12 Sep for print!) | 3.4 | Signed commitments + fulfillment tracker | ≥60% of budget covered by 19 Sep | Not started | Logos arriving after print freeze — hard cutoff 12 Sep
P3 Funding & Sponsorship | 3.8 | Sponsor recognition assets to design | Fascia/backdrop logos must hit the print files | P1 | 2026-09-11 | 2026-09-12 | Sponsorship → Design | Vector logos + tier placement map | 3.4 | Logo pack to design | In v2 print files 12 Sep | Not started
P4 Pavilion Design & Branding | 4.1 | Confirm technical envelope from exhibitor manual | Design must fit reality: dimensions (A2), walls, power, height, open sides | P1 | 2026-09-08 | 2026-09-09 | Design Lead + Liaison | Read manual (from 1.2); site plan from ECG; resolve Assumption A2 | 1.2 | Tech spec 1-pager | Spec confirmed 9 Sep | Not started | Manual delay blocks design freeze
P4 Pavilion Design & Branding | 4.2 | Pavilion identity: "Made in GB" concept | One strong story — an ecosystem, not 10 booths | P1 | 2026-09-08 | 2026-09-10 | Design Lead | Identity: name, palette (mountain motif), message hierarchy: GB = emerging tech ecosystem → 10 proof-point companies; align with P@SHA "Made in GB" language | 1.1 | Concept board approved | PD sign-off 10 Sep | Not started | Over-design vs 3-day build reality
P4 Pavilion Design & Branding | 4.3 | Zone plan for ~90 m² | Traffic flow decides lead volume | P1 | 2026-09-09 | 2026-09-11 | Design Lead | Zones: reception/info desk, 10 uniform company pods, meeting corner (6 pax), GB ecosystem wall, demo screen, media/photo spot, lockable storage | 4.1 | Dimensioned zone plan | Fits confirmed dims; approved 11 Sep | Not started
P4 Pavilion Design & Branding | 4.4 | GB ecosystem infographic wall | Credibility for investors/officials in 30 seconds | P1 | 2026-09-10 | 2026-09-12 | Design + Comms | Stats from P@SHA diagnostic ($15–18M sector, 3–4k freelancers, ~120 active firms, STPs, $4.6B national exports); map of GB tech geography; QR to ecosystem page | 4.2 | Wall artwork in print pack | In v2 files 12 Sep | Not started | Cite sources on the wall itself
P4 Pavilion Design & Branding | 4.5 | Company pod graphics — uniform template | Equal visibility, coherent brand | P1 | 2026-09-10 | 2026-09-13 | Design Lead | Template: logo, one-line value prop, 3 service icons, QR to profile/lead form | 2.5 | 10 pod artworks | All 10 in print pack 13 Sep | Not started | Missing assets → template fallback
P4 Pavilion Design & Branding | 4.6 | Digital assets: 3-min loop video + slide loop | Motion pulls walk-by traffic | P2 | 2026-09-10 | 2026-09-17 | Comms Lead | Cut from existing company footage + stats; export for venue screens | 2.5 | Loop files on 2 USBs + cloud | Playing on screens 21 Sep | Not started
P4 Pavilion Design & Branding | 4.7 | Lead-gen mechanics build | Every visitor must be capturable in <30 seconds | P1 | 2026-09-10 | 2026-09-14 | BD Lead + Design | Central QR → form (name/org/interest/company); per-company QR; badge-photo protocol; paper fallback pads; nightly export to Lead Tracker | 4.3 | Working QR system + fallback | End-to-end test passed 15 Sep | Not started | Venue internet — offline-capable form
P4 Pavilion Design & Branding | 4.8 | Print production in KARACHI + proofing | Printing in GB and freighting = weather/freight risk; print where you exhibit | P1 | 2026-09-12 | 2026-09-20 | Design + Logistics | Vendor selected 12 Sep; proofs approved 15 Sep; production 16–19 Sep; delivery to venue 20 Sep | 4.4/4.5 | All print delivered to booth | Zero reprints needed 21 Sep | Not started | Vendor slip — penalty clause + backup vendor
P4 Pavilion Design & Branding | 4.9 | Furniture/AV orders via ECG contractor | Screens, counters, stools, lockable cabinet beyond shell scheme | P1 | 2026-09-11 | 2026-09-15 | Logistics Lead | Order from exhibitor manual rate card; confirm delivery to stand 20 Sep | 2.7/4.3 | Order confirmations | Delivered on setup day 1 | Not started
P4 Pavilion Design & Branding | 4.10 | MOU-signing / photo moment setup | Media-ready moments multiply reach | P2 | 2026-09-12 | 2026-09-20 | Design Lead | Backdrop doubles as signing/photo wall; small signing table staged in meeting corner | 4.3 | Signing corner ready | Used for ≥5 signings/photo-ops | Not started
P5 Stakeholder Engagement | 5.1 | Build the invite list (Stakeholder Database) | The right 60 people at the pavilion beat 6,000 walk-bys | P1 | 2026-09-08 | 2026-09-10 | Stakeholder Lead | Categories: federal (MoITT, PSEB, Ignite, TDAP, SIFC, NITB), GB govt (CM office, IT minister, Secretary IT), P@SHA leadership, industry CEOs, investors/VCs, dev orgs (AKF, UNDP, WB), diplomats via TDAP/ECG international program, media | 1.3 | ≥60-row database, prioritized A/B/C | List locked 10 Sep | Not started
P5 Stakeholder Engagement | 5.2 | Verify current officeholders before invitations | Aug 2026 saw churn (P@SHA vote; new GB cabinet; new PSEB/Ignite CEOs) | P1 | 2026-09-09 | 2026-09-10 | Stakeholder Lead | Check official sites/calls (Assumption A11) | 5.1 | Verified names | Zero mis-addressed letters | Not started
P5 Stakeholder Engagement | 5.3 | Draft invitation letters + 1-page pavilion brief | Professional ask with a reason to come | P1 | 2026-09-10 | 2026-09-11 | Stakeholder + Comms | Letter (PD signature) + brief: what GB pavilion is, who exhibits, what to see, suggested slot | 5.1 | Letter pack | Ready 11 Sep | Not started
P5 Stakeholder Engagement | 5.4 | Dispatch invitations via weight-bearing channels | Channels carry credibility: P@SHA secretariat, ECG protocol office, GB govt liaison | P1 | 2026-09-11 | 2026-09-14 | Liaison + Stakeholder | Federal via P@SHA/ECG; GB govt via Secretary IT; diplomats via TDAP; VCs direct + LinkedIn | 5.3 | All A-list invites delivered | 100% A-list invited by 14 Sep | Not started | Follow up B-list 16 Sep
P5 Stakeholder Engagement | 5.5 | Confirm VIP visit slots into show-day schedule; assign hosts | Managed moments, not ambush tours | P1 | 2026-09-15 | 2026-09-21 | Stakeholder Lead | Slot grid on Gov-VIP sheet; one host + one photographer per visit; align Day-1 slots with official opening protocol | 5.4 | Confirmed VIP schedule | ≥8 confirmed visits | Not started
P5 Stakeholder Engagement | 5.6 | Talking points & specific ask per VIP | Every visit must produce something: a subsidy, an intro, a commitment | P1 | 2026-09-14 | 2026-09-19 | PD + Stakeholder | E.g. PSEB: recurring expo subsidy for GB firms; GB govt: year-2 co-funding; SIFC: GB in national programs; TDAP: GITEX slot for GB firm | 5.5 | 1-page per A-list VIP | Ask made in ≥6 visits | Not started
P5 Stakeholder Engagement | 5.7 | Protocol kit: welcome flow, guestbook, GB souvenir, photo moment, 60-sec tour script | Memorable ≠ expensive | P2 | 2026-09-15 | 2026-09-20 | Stakeholder Lead | GB handicraft souvenir; trained reception; tour script rehearsed | 5.5 | Kit at reception desk | Used every visit | Not started
P5 Stakeholder Engagement | 5.8 | Execute visits; log; same-day thank-you + social post | Capture value while warm | P1 | 2026-09-22 | 2026-09-24 | Stakeholder + Comms | Log in Gov-VIP sheet; photo → post within 4h; thank-you within 24h | 5.5 | Visit log complete | 100% VIPs logged & thanked | Not started
P6 Business Development & B2B | 6.1 | Each company builds a 20-account target list | Meetings are made before the show, not at it | P1 | 2026-09-09 | 2026-09-12 | BD Lead → companies | Template on B2B sheet: clients, partners, investors; mined from exhibitor list + networks | 2.4 | 200-account pool | 10/10 lists complete 12 Sep | Not started | Coach laggards at standup
P6 Business Development & B2B | 6.2 | Central pavilion-level target lists: investors, buyers, international delegates | Some doors open only at ecosystem level | P1 | 2026-09-10 | 2026-09-13 | BD Lead | VC/angel list; corporate buyers; 350+ intl delegates program via ECG/TDAP | 5.1 | 3 central lists | ≥50 central targets | Not started
P6 Business Development & B2B | 6.3 | Obtain exhibitor/delegate list from ECG | Precision beats scanning badges | P1 | 2026-09-09 | 2026-09-12 | PASHA/ECG Liaison | Request with pavilion confirmation; mine for matches per company | 1.2 | List distributed | In companies' hands 12 Sep | Not started | If refused: build from public exhibitor page
P6 Business Development & B2B | 6.4 | Meeting-request outreach wave | Fill the calendar before doors open | P1 | 2026-09-12 | 2026-09-19 | BD Lead + companies | Email/LinkedIn/P@SHA intros; template scripts; track in B2B log | 6.1 | Requests sent ≥150 | ≥40 meetings booked pre-show | Not started
P6 Business Development & B2B | 6.5 | Build the 3-day meeting calendar | Two concurrent 45-min slots; no double-booking; VIP slots protected | P1 | 2026-09-13 | 2026-09-20 | BD Lead | Grid on B2B sheet; meeting corner capacity 2×6 pax; buffer slots for walk-ins | 6.4 | Published calendar v1 | <10% slot conflicts | Not started
P6 Business Development & B2B | 6.6 | Meeting kit per company | Convert the meeting, not just hold it | P1 | 2026-09-12 | 2026-09-16 | BD Lead | Pitch, 1-pager, pricing sheet, 2 case studies, follow-up email template | 2.5 | 10 kits ready | Checked at rehearsal 16 Sep | Not started
P6 Business Development & B2B | 6.7 | Lead qualification standard trained to all reps | Comparable data or the funnel lies | P1 | 2026-09-15 | 2026-09-17 | BD Lead | Hot/Warm/Cold + BANT-lite (budget, authority, need, timeline); practice at rehearsal | 2.8 | 20 reps trained | 100% pass mini-quiz | Not started
P6 Business Development & B2B | 6.8 | Show-time B2B operation | Slot discipline + daily lead sync | P1 | 2026-09-22 | 2026-09-24 | BD Lead | Meeting-desk owner per shift; 18:30 lead sync: export QR form → Lead Tracker, qualify, assign | 6.5 | Daily synced tracker | ≥40 meetings held; ≥150 leads | Not started
P6 Business Development & B2B | 6.9 | Assign every lead an owner + follow-up date BEFORE leaving Karachi | Follow-up decay kills 80% of expo value | P1 | 2026-09-24 | 2026-09-25 | BD + PMO | Final sync 24 Sep 18:30 + 25 Sep morning: every lead has owner + due date in tracker | 6.8 | Zero unassigned leads | 100% assigned by 25 Sep | Not started
P7 MOU & Partnership Mgmt | 7.1 | Scan pipeline for MOU candidates | Aim signings; don't hope for them | P1 | 2026-09-10 | 2026-09-13 | PD + BD Lead | Sources: delegation history, CXO meetup contacts, sponsor talks, B2B outreach replies | 6.1 | Candidate list (≈8) | ≥8 candidates 13 Sep | Not started
P7 MOU & Partnership Mgmt | 7.2 | Qualify 3–5 realistic MOUs; align scope with counterparts | No surprise-MOUs — agree substance pre-event | P1 | 2026-09-13 | 2026-09-17 | PD | Calls with counterparts; agree purpose, commitments, signatories | 7.1 | Agreed term sheets | 3–5 MOUs pre-agreed 17 Sep | Not started | Vanity MOUs — each must name a next action
P7 MOU & Partnership Mgmt | 7.3 | Prepare draft MOUs + light legal review | Sign-ready documents, 2 copies, folders | P1 | 2026-09-14 | 2026-09-19 | PMO / Follow-up Lead | Standard template; company-specific fill-ins; printed in Karachi | 7.2 | Signing-ready drafts | Zero drafting at the venue | Not started
P7 MOU & Partnership Mgmt | 7.4 | Schedule signing ceremony slots with media + witnesses | Visibility multiplies partnership value | P2 | 2026-09-17 | 2026-09-21 | Stakeholder + Comms | Suggested: Day 2 (23 Sep) 15:00 block; P@SHA/official witness; photographer briefed | 7.2/5.5 | Ceremony schedule | ≥3 signings with media coverage | Not started
P7 MOU & Partnership Mgmt | 7.5 | Record every commitment: owner, 30-day action, conversion stage | An MOU is a start line, not a trophy | P1 | 2026-09-22 | 2026-09-25 | PMO / Follow-up Lead | MOU tracker: parties, commitments, owner, 30-day action, stage (meeting→opportunity→proposal→contract→revenue) | 7.4 | Tracker complete before departure | 100% signed MOUs have owner + 30-day action | Not started
P7 MOU & Partnership Mgmt | 7.6 | 30/60/90 conversion reviews | MOU → business or it was theatre | P1 | 2026-10-24 | 2026-12-23 | PMO / Follow-up Lead | Review at 24 Oct / 23 Nov / 23 Dec: advance stage or mark dormant with reason | 7.5 | Conversion report per review | ≥2 MOUs at proposal+ by day 60; ≥1 contract by day 90 | Not started
P8 Social Media, PR & Media | 8.1 | Comms plan: platforms, hashtags, voice, roles | Coherent voice from day one | P1 | 2026-09-05 | 2026-09-06 | Comms Lead | LinkedIn (B2B primary), Facebook (GB community), Instagram (visual), X (news), YouTube (video); #MadeInGB #GBPavilion #ITCNAsia2026; calendar on Social sheet | 1.3 | Comms plan approved | Calendar live 6 Sep | Not started
P8 Social Media, PR & Media | 8.2 | Announcement: GB pavilion at ITCN Asia Karachi | Ride the existing "Made in GB" narrative momentum | P1 | 2026-09-06 | 2026-09-08 | Comms Lead | Post + P@SHA/GBSHA amplification request; tag stakeholders | 8.1 | Announcement live | ≥10k combined reach (est.) | Not started
P8 Social Media, PR & Media | 8.3 | 10 company spotlight posts | Every company enters the show already visible | P1 | 2026-09-12 | 2026-09-21 | Comms Lead | 1/day from assets (2.5); company amplification kit (same-day reshare) | 2.5 | 10 spotlights published | 10/10 by 21 Sep | Not started
P8 Social Media, PR & Media | 8.4 | Countdown + founder stories + delegation journey | The Gilgit→Karachi journey IS the story — use it | P2 | 2026-09-15 | 2026-09-21 | Comms Lead | D-7…D-1 countdown; founder quotes; travel-day content (KKH/airport) | 8.1 | Daily content D-7 onward | Posted daily | Not started
P8 Social Media, PR & Media | 8.5 | Press kit + release to tech/business media | Earned media = third-party credibility | P1 | 2026-09-15 | 2026-09-20 | Comms Lead | Release: "first GB pavilion at ITCN Asia Karachi"; targets: ProPakistani, TechJuice, Business Recorder, Dawn, APP, Pamir Times + GB outlets; offer founder interviews | 8.1 | Kit sent to ≥10 outlets | ≥3 pre-event mentions | Not started | Embargo until pavilion confirmed in writing
P8 Social Media, PR & Media | 8.6 | Live coverage: daily posts, VIP visits, signings, reels; photo/video team | Show-time visibility feeds the report and year-2 sales | P1 | 2026-09-18 | 2026-09-24 | Comms Lead | Photographer/videographer booked by 12 Sep; shot list; 2 posts/day minimum + stories; same-day VIP/MOU posts | 8.1 | Daily coverage live | ≥15 posts across 3 days | Not started
P8 Social Media, PR & Media | 8.7 | On-site media interviews | Pitch outlets present at ITCN | P2 | 2026-09-22 | 2026-09-24 | Comms Lead | Media desk list from ECG; founders prepped (2.8) | 8.5 | ≥5 interviews | ≥5 recorded/aired | Not started
P8 Social Media, PR & Media | 8.8 | Post-event: results release, thank-yous, 10 success stories, wrap video, coverage log | Cement the narrative; feed the impact report | P1 | 2026-09-25 | 2026-10-15 | Comms Lead | Results release 29 Sep; 10 stories by 15 Oct; wrap video 10 Oct; coverage log to Post-Event Report | 10.9 | Post-event pack | ≥8 earned mentions total | Not started
P9 Logistics | 9.1 | Delegate manifest + passes submission to ECG | No pass, no entry | P1 | 2026-09-09 | 2026-09-12 | Logistics Lead | Manifest on Logistics sheet (names, CNIC, phones); submit per exhibitor manual | 2.6 | Passes confirmed | 25 passes issued by 18 Sep | Not started
P9 Logistics | 9.2 | Travel plan & bookings — with weather math | GIL–ISB flies Fri/Sat/Sun only (48-seat ATR) and cancels often; Karachi requires ISB connection | P1 | 2026-09-05 | 2026-09-11 | Logistics Lead | Wave plan on Logistics sheet: main wave GIL→ISB Fri 18 Sep + NATCO road fallback same night; Skardu contingent via jet service; ISB→KHI 19–20 Sep; ALL in Karachi by 20 Sep 18:00 | 3.1 | Tickets + fallback bookings | 100% delegates booked by 11 Sep | Not started | Weather — see Risk R1
P9 Logistics | 9.3 | Hard weather-contingency rule adopted | Decide the fallback BEFORE the cancellation | P1 | 2026-09-11 | 2026-09-12 | Logistics Lead | Rule: if Fri 18 Sep GIL flight cancels → road departure same evening (arrive ISB 19 Sep) → KHI 20 Sep; Skardu jets as plan-B seats | 9.2 | Rule circulated & acknowledged | Zero delegates stranded | Not started
P9 Logistics | 9.4 | Hotel block + van hire in Karachi | Cohesion and punctuality; near Expo Centre (University Rd/Gulshan side) | P1 | 2026-09-08 | 2026-09-12 | Logistics Lead | ~13 rooms 19/20–25 Sep; 2 vans (14-seat) with drivers; airport pickups scheduled | 3.1 | Confirmations on file | Rooms+vans confirmed 12 Sep | Not started
P9 Logistics | 9.5 | Equipment kit | Self-sufficiency at the booth | P1 | 2026-09-12 | 2026-09-17 | Logistics Lead | Laptops/demo devices per company, chargers, extension leads, HDMI, 2 hotspot routers + Jazz/Zong SIMs (SCOM unreliable down-country), cleaning kit, first aid, stationery, cash float | 2.7 | Packed kit checklist signed | Nothing bought in panic at venue | Not started
P9 Logistics | 9.6 | Materials plan: print delivery + storage | Everything at the stand on setup day 1 | P1 | 2026-09-15 | 2026-09-20 | Logistics + Design | Karachi print vendor delivers to venue 20 Sep 10:00; lockable cabinet; APT Showfreight only if anything ships from GB | 4.8 | Delivery confirmations | All materials at stand 20 Sep noon | Not started
P9 Logistics | 9.7 | On-site services: power, internet, cleaning, security check | Booth uptime | P2 | 2026-09-20 | 2026-09-21 | Logistics Lead | Verify against orders on setup days; venue wifi test; escalation contact at ECG ops | 4.9 | Services live | Zero downtime on Day 1 | Not started
P9 Logistics | 9.8 | Emergency & safety sheet | Boring until it isn't | P2 | 2026-09-15 | 2026-09-18 | Logistics Lead | ECG office +92-21-38709970, venue security, nearest hospital (Aga Khan University Hospital), committee numbers, embassy n/a (domestic), delegate medical notes (voluntary) | 9.1 | Card in every delegate pack | Distributed 20 Sep | Not started
P9 Logistics | 9.9 | Return travel + materials back-haul/disposal | Clean exit; save reusables for Lahore Jan 2027 | P2 | 2026-09-20 | 2026-09-25 | Logistics Lead | Return bookings 25–27 Sep; reusable branding stored in Karachi (P@SHA/ECG or vendor) for year-2 | 9.2 | Return manifest; storage receipt | Reusables stored, not trashed | Not started
P10 ITCN Execution | 10.1 | Advance party in Karachi | De-risk setup: prints, venue access, orders | P1 | 2026-09-19 | 2026-09-19 | Logistics Lead | 2 pax arrive 19 Sep: vendor check, venue access passes, contractor confirmations | 9.2 | Advance report to standup | All green before main wave lands | Not started
P10 ITCN Execution | 10.2 | Setup day 1: structure, branding, furniture, power | Physical build | P1 | 2026-09-20 | 2026-09-20 | Design + Logistics | Install backdrop/fascia/pods; furniture placed; power tested; prints received | 10.1 | Pavilion 80% built | Built by 20 Sep 20:00 | Not started
P10 ITCN Execution | 10.3 | Setup day 2: dress pods, screens, lead-system test, walkthrough, briefing dinner | Show-ready + team aligned | P1 | 2026-09-21 | 2026-09-21 | Project Director | Full walkthrough vs checklist; in-situ pitch run; QR live test; evening delegation briefing dinner: roles, rota, VIP schedule, targets | 10.2 | Sign-off photo set; briefing held | 100% checklist green 21 Sep 18:00 | Not started
P10 ITCN Execution | 10.4 | Daily operating rhythm | The pavilion runs on rhythm, not memory | P1 | 2026-09-22 | 2026-09-24 | Project Director | 08:30 hotel briefing (targets, VIPs, slots) → 10:00 doors → shift rota → 18:30 debrief: leads synced, meetings logged, issues, next-day plan | 10.3 | Daily briefs + debriefs held | 6/6 held on time | Not started
P10 ITCN Execution | 10.5 | Day 1 (22 Sep): opening + VIP day | First impressions; official protocol | P1 | 2026-09-22 | 2026-09-22 | Stakeholder Lead | Align with official opening; VIP tours per schedule; media day; evening: post Day-1 highlights | 5.5 | VIP visits logged | ≥4 VIP visits Day 1 | Not started
P10 ITCN Execution | 10.6 | Day 2 (23 Sep): B2B peak + MOU ceremony | Business day | P1 | 2026-09-23 | 2026-09-23 | BD Lead | Max meeting density; investor slots; 15:00 MOU signings + press; optional GB networking dinner evening | 6.5/7.4 | Meetings + signings done | ≥15 meetings; ≥3 signings | Not started
P10 ITCN Execution | 10.7 | Day 3 (24 Sep): international focus + strong close | Finish strong, capture everything | P1 | 2026-09-24 | 2026-09-24 | Project Director | International delegates focus; remaining meetings; closing content; thank-yous; teardown prep; final lead sync | 10.4 | Day-3 report; leads 100% assigned | ≥150 total leads by close | Not started
P10 ITCN Execution | 10.8 | Pavilion command structure live | Clarity under pressure | P1 | 2026-09-19 | 2026-09-21 | Project Director | PD (overall) / Floor Manager per shift / Meeting Desk / Reception / Media / Runner; rota on Logistics sheet; walkie/WhatsApp discipline | 1.3 | Rota published | Every hour covered | Not started
P10 ITCN Execution | 10.9 | Daily report to committee + P@SHA | Accountability builds year-2 support | P1 | 2026-09-22 | 2026-09-24 | PMO / Follow-up Lead | Nightly 1-pager: leads #, meetings #, VIPs, media, issues | 10.4 | 3 daily reports | Sent by 21:00 each day | Not started
P10 ITCN Execution | 10.10 | Dismantle, debrief, store, depart | Clean close protects assets & goodwill | P1 | 2026-09-25 | 2026-09-25 | Logistics Lead | 25 Sep: teardown, storage handover (9.9), venue clearance, hot-wash debrief (30 min), departures | 10.7 | Clearance + debrief notes | No venue penalties; debrief captured | Not started
P11 Post-Event Follow-Up | 11.1 | 48-hour thank-you wave | Warm while hot: every lead, VIP, sponsor, partner | P1 | 2026-09-25 | 2026-09-27 | PMO + companies | Personalized emails from lead owners; VIP letters from PD; sponsor thank-yous with photo | 6.9 | 100% thank-yous sent | By 27 Sep | Not started
P11 Post-Event Follow-Up | 11.2 | 7-day close-out: leads worked, retro, results release, report v1 | Institutional memory + public proof | P1 | 2026-09-28 | 2026-10-02 | PMO / Follow-up Lead | First contact on all leads; internal retro (what to fix for Lahore); results press release; Post-Event Report v1 | 11.1 | Report v1 + release | By 2 Oct | Not started
P11 Post-Event Follow-Up | 11.3 | Sponsor fulfillment report | Renewals for year-2 start here | P1 | 2026-10-02 | 2026-10-09 | Sponsorship Lead | Per-sponsor: photos, reach, VIP visits, mentions delivered | 11.2 | Reports delivered | 100% sponsors reported by 9 Oct | Not started
P11 Post-Event Follow-Up | 11.4 | 30-day review (24 Oct) | Conversion discipline checkpoint 1 | P1 | 2026-10-24 | 2026-10-24 | PMO / Follow-up Lead | 100% leads contacted; meetings booked; proposals out; MOU 30-day actions done; update funnel numbers | 11.2 | 30-day scorecard | See 30-60-90 sheet targets | Not started
P11 Post-Event Follow-Up | 11.5 | 60-day review (23 Nov) + YEAR-2 DECISION | Lahore 29–31 Jan 2027 is ~2 months later — decide and book now | P1 | 2026-11-23 | 2026-11-23 | Project Director | Pipeline review; 3 case studies; decide Lahore participation, size, improvements; confirm booking with ECG; open company selection round 2 | 11.4 | Year-2 decision memo + booking | Booked by 30 Nov | Not started
P11 Post-Event Follow-Up | 11.6 | 90-day review (23 Dec): impact report + stakeholder debrief | Close the loop; make the case for year 2–3 support | P1 | 2026-12-23 | 2026-12-23 | Project Director | Impact report (revenue, contracts, jobs, media reach); debrief with P@SHA/ECG, GB govt, sponsors; publish public impact story | 11.5 | Published impact report | See KPIs sheet | Not started
P11 Post-Event Follow-Up | 11.7 | Lessons-learned → year-2 master plan | Each ITCN must be stronger than the last | P2 | 2026-12-01 | 2026-12-23 | Project Director | Clone this workbook for Lahore Jan 2027; carry forward stakeholder DB, lead tracker, sponsor relationships | 11.5 | Year-2 workbook v1 | Ready before 1 Jan 2027 | Not started
Owners are roles (see Committee & Governance). Dates are 2026. P7/P11 review dates: 24 Oct (30-day), 23 Nov (60-day), 23 Dec (90-day) — counted from dismantle day 25 Sep.

## Daily Action Plan Sep 3-18
DAILY ACTION PLAN — THE 16-DAY SPRINT (3–18 SEP 2026)
D-minus counts to opening day (22 Sep). This sheet drives the daily 18:00 standup: read today's block, mark Done?, move slippage to tomorrow WITH a note. Travel begins 18 Sep; setup 19–21 Sep; show 22–24 Sep.
Date | Day | D- | Focus of the day | # | Action | Owner | Output / deliverable | Done? | Notes
2026-09-03 | Thu | D-19 | Kickoff & governance | 1 | Hold kickoff: ratify objectives, KPI targets, delegation size (A4), cost-share basis (A6) | Project Director | Objectives memo
|  |  |  | 2 | Send written-confirmation request to ECG/Umair Nizam office (space, inclusions, passes, 3-yr frame); request exhibitor manual | PASHA/ECG Liaison | Email sent, on file
|  |  |  | 3 | Fill committee roles; open WhatsApp groups, shared drive; adopt this workbook as master | PD + PMO | Committee sheet complete; channels live
|  |  |  | 4 | Set daily 18:00 standup (recurring, Sep 3–21) | Project Director | Invites accepted
|  |  |  | 5 | Draft company criteria + application form (from rubric) | Companies Lead | Form ready for review
2026-09-04 | Fri | D-18 | Mobilization opens | 1 | Approve criteria; GBSHA co-sign; LAUNCH call for applications (deadline 7 Sep 23:59) | Companies Lead + GBSHA | Form live + announcement out
|  |  |  | 2 | Push call through GBSHA, SCO STPs (Gilgit/Skardu/Hunza), KIU incubator, WhatsApp groups | Companies Lead | ≥120 companies reached
|  |  |  | 3 | Start cost model: request quotes (PIA/NATCO, ISB–KHI fares, hotels, Karachi printers, vans, AV) | Sponsorship + Logistics | Quote requests out
|  |  |  | 4 | Draft sponsorship tiers + hit-list; book wave-1 intro calls via P@SHA | Sponsorship Lead | Tier draft + call slots
|  |  |  | 5 | Chase ECG confirmation if no reply; PD phone call | PASHA/ECG Liaison | Reply or escalation done
2026-09-05 | Sat | D-17 | Money & message | 1 | Ratify sponsorship tiers & pricing (A10); finalize 2-page sponsor deck | Sponsorship Lead | Deck PDF v1
|  |  |  | 2 | Ratify comms plan: platforms, hashtags (#MadeInGB #GBPavilion #ITCNAsia2026), calendar | Comms Lead | Social sheet calendar live
|  |  |  | 3 | Direct outreach to 15 strongest candidate companies (do not rely on the form alone) | Companies Lead | 15 conversations logged
|  |  |  | 4 | Receive ECG confirmation / exhibitor manual; extract deadlines into this workbook | PASHA/ECG Liaison | Terms on file (A1 resolved)
|  |  |  | 5 | Scan travel availability for 18–20 Sep (PIA GIL–ISB Fri/Sat/Sun; NATCO; ISB–KHI fares) | Logistics Lead | Options memo
2026-09-06 | Sun | D-16 | Community alignment | 1 | Run community info session (evening Zoom): opportunity, criteria, costs, obligations | Companies Lead | ≥40 attendees; recording shared
|  |  |  | 2 | Ratify budget v1 with real quotes; ratify cost-share policy; publish to community (A5/A6 resolved) | Steering Committee | Budget v1 + policy note
|  |  |  | 3 | Publish announcement post + request P@SHA/GBSHA amplification | Comms Lead | Announcement live
|  |  |  | 4 | Confirm internal history: which edition did the first delegation attend (A3); collect photos/outcomes for narrative | Project Director | Baseline note for KPIs sheet
2026-09-07 | Mon | D-15 | Applications close | 1 | Applications close 23:59; log all applicants | Companies Lead | Applicant register
|  |  |  | 2 | Wave-1 sponsor asks delivered: GB IT Dept, PSEB (cite P@SHA diagnostic subsidy recommendation), SCO, AKF/Accelerate Prosperity | Sponsorship + PD | 4 asks delivered
|  |  |  | 3 | Selection panel convenes; begin scoring | Selection Panel | Scoring underway
|  |  |  | 4 | Draft stakeholder invite list skeleton (categories + known names) | Stakeholder Lead | Draft DB ≥40 rows
2026-09-08 | Tue | D-14 | Selection day | 1 | Finish scoring by 12:00; select 10 + 2 reserves; PD ratifies | Selection Panel | Signed selection minute
|  |  |  | 2 | Notify selected/reserve/regret applicants (regrets get year-2 waitlist offer) | Companies Lead | All notified same day
|  |  |  | 3 | Read exhibitor manual: confirm dimensions (A2), inclusions (A8), passes (A7), contractor rate card | Design + Logistics | Tech spec 1-pager
|  |  |  | 4 | Design kickoff: "Made in GB" identity concept work starts | Design Lead | Concept drafts due 10 Sep
|  |  |  | 5 | Hotel + van quotes shortlisted; hold rooms near Expo Centre | Logistics Lead | Holds placed
2026-09-09 | Wed | D-13 | Onboarding & assets | 1 | Company onboarding call: expectations, asset checklist (due 12 Sep), 20-target B2B homework (due 12 Sep), commitment forms signed | Companies Lead | 10 signed forms
|  |  |  | 2 | Collect rep names + CNIC; start pass manifest | Logistics Lead | Manifest 50%+
|  |  |  | 3 | Exhibition-needs survey out (power, screens, demo gear) | Companies Lead | Survey out
|  |  |  | 4 | Request exhibitor/delegate list from ECG for B2B mining | PASHA/ECG Liaison | Request sent
|  |  |  | 5 | MOU pipeline scan starts: list candidate partnerships from delegation/CXO/sponsor contacts | PD + BD Lead | Candidate list draft
2026-09-10 | Thu | D-12 | Design & targets | 1 | Approve pavilion identity concept; start zone plan for confirmed dimensions | Design Lead | Concept signed off
|  |  |  | 2 | Ecosystem-wall content drafted (P@SHA diagnostic stats, GB map, QRs) | Design + Comms | Wall draft
|  |  |  | 3 | Stakeholder DB locked (≥60 rows, A/B/C priority); verify officeholders (A11) | Stakeholder Lead | Verified DB
|  |  |  | 4 | Central investor/buyer/international target lists started | BD Lead | Lists ≥50% built
|  |  |  | 5 | Wave-1 sponsor follow-up meetings held | Sponsorship Lead | ≥2 meetings done
2026-09-11 | Fri | D-11 | Book everything | 1 | BOOK all travel: GIL→ISB Fri 18 Sep + road fallback; Skardu jets; ISB→KHI 19–20 Sep; adopt weather rule | Logistics Lead | Tickets issued; rule circulated
|  |  |  | 2 | Confirm hotel block + 2 vans (19/20–25 Sep) | Logistics Lead | Confirmations on file
|  |  |  | 3 | Zone plan approved; furniture/AV order list built from needs survey | Design + Logistics | Order list ready
|  |  |  | 4 | Invitation letters + 1-page pavilion brief finalized | Stakeholder + Comms | Letter pack ready
|  |  |  | 5 | Sponsor logo cutoff notice: vectors due tomorrow for print files | Sponsorship Lead | Sponsors informed
2026-09-12 | Sat | D-10 | Design freeze | 1 | ASSET FREEZE: all company logos/profiles/1-pagers in (late = template pod) | Companies Lead | Asset folder 10/10
|  |  |  | 2 | Design v2 with sponsor logos; SIGN-OFF; release print files to Karachi vendor | Design Lead | Print files released
|  |  |  | 3 | Select Karachi print vendor (backup named); delivery-to-venue 20 Sep in PO | Design + Logistics | PO issued
|  |  |  | 4 | Company spotlight posts begin (1/day to 21 Sep) | Comms Lead | Spotlight #1 live
|  |  |  | 5 | Passes manifest submitted to ECG; B2B 20-target lists due from all companies | Logistics + BD | Manifest sent; 200-account pool
|  |  |  | 6 | Book photographer/videographer for 20–24 Sep | Comms Lead | Booking confirmed
2026-09-13 | Sun | D-9 | Pipeline day | 1 | Consolidate B2B pool; de-duplicate; assign pavilion-level targets | BD Lead | Target pool final
|  |  |  | 2 | Meeting-request outreach wave starts (email/LinkedIn/P@SHA intros) | BD + companies | ≥60 requests out
|  |  |  | 3 | Qualify MOU candidates to 3–5; open scope talks with counterparts | Project Director | Term-sheet talks started
|  |  |  | 4 | Meeting calendar grid built (2 concurrent 45-min slots × 3 days) | BD Lead | Calendar v0
|  |  |  | 5 | Press kit + release drafted | Comms Lead | Draft for review
2026-09-14 | Mon | D-8 | Invitations out | 1 | Dispatch A-list VIP invitations via P@SHA secretariat / ECG protocol / GB Secretary IT channels | Stakeholder + Liaison | A-list 100% invited
|  |  |  | 2 | VIP talking points + specific asks drafted per A-list target | PD + Stakeholder | Ask sheet v1
|  |  |  | 3 | Sponsor wave-2 follow-ups; close pending wave-1 | Sponsorship Lead | Status per target updated
|  |  |  | 4 | Lead-gen build: central QR form + per-company QRs + paper fallback | BD + Design | System draft ready
2026-09-15 | Tue | D-7 | Rehearsal 1 & countdown | 1 | Pitch rehearsal #1 (all 10, in person or video): 3-min pitch + demo; feedback | BD + Comms | Scorecards; fixes listed
|  |  |  | 2 | Countdown content D-7 starts; founder-story posts | Comms Lead | Daily countdown live
|  |  |  | 3 | Print proofs approved (colors, spelling, logos!) | Design Lead | Proof sign-off
|  |  |  | 4 | Furniture/AV order placed with ECG contractor; delivery 20 Sep confirmed | Logistics Lead | Order confirmation
|  |  |  | 5 | Press release to media list (≥10 outlets); interview offers | Comms Lead | Kit sent
|  |  |  | 6 | MOU drafts to counterparts for review | PMO / Follow-up | Drafts circulating
2026-09-16 | Wed | D-6 | Rehearsal 2 & meetings | 1 | Pitch rehearsal #2 + media training (do/don't, soundbites) | BD + Comms | 10/10 rehearsed twice
|  |  |  | 2 | Meeting kits per company checked (pitch, 1-pager, pricing, cases, follow-up template) | BD Lead | 10 kits verified
|  |  |  | 3 | Meeting calendar v1 published; confirmations chased (target ≥40 booked) | BD Lead | Calendar shared
|  |  |  | 4 | B-list invitations + A-list RSVPs chased | Stakeholder Lead | RSVP log updated
|  |  |  | 5 | Equipment kit packing starts (laptops, leads, HDMI, hotspots, SIM plan, first aid) | Logistics Lead | Kit checklist 60%
2026-09-17 | Thu | D-5 | Go/No-Go | 1 | GO/NO-GO review across all workstreams vs checklist; unresolved ambers escalated | Steering Committee | Go decision minuted
|  |  |  | 2 | Lead-capture end-to-end test with 5 reps (QR → form → tracker export) | BD Lead | Test passed
|  |  |  | 3 | Reps briefed on show playbook: lead flow, etiquette, rota, dress code | BD Lead | Playbook acknowledged ×20
|  |  |  | 4 | MOU drafts finalized; signing slots proposed to counterparts (Day 2, 15:00) | PMO + Stakeholder | 3–5 sign-ready MOUs
|  |  |  | 5 | Emergency card printed; delegate packs assembled (passes plan, schedule, contacts) | Logistics Lead | Packs ready
2026-09-18 | Fri | D-4 | Wheels up | 1 | MAIN TRAVEL WAVE: GIL→ISB PIA morning; if cancelled → NATCO road tonight (weather rule live) | Logistics Lead | Wave A/B status report
|  |  |  | 2 | Advance-party final checklist for Karachi (prints, venue access, contractor recon) | Logistics Lead | Advance brief done
|  |  |  | 3 | Countdown D-4 + journey content (airport/KKH) | Comms Lead | Posts live
|  |  |  | 4 | Standup moves to travel mode (WhatsApp); tracker handover to on-ground PMO | PMO / Follow-up | Continuity confirmed
|  |  |  | 5 | Final VIP slot confirmations into show schedule | Stakeholder Lead | VIP grid v1 frozen
Sep 19–25 continues on the Master Timeline (Phase 10) and the show-day plan in B2B/Gov-VIP sheets: 19 Sep advance party · 20–21 Sep setup · 22–24 Sep show · 25 Sep dismantle & depart.

## Weekly Targets
WEEKLY TARGETS — KICKOFF TO 90-DAY REVIEW
Each week has 3–6 make-or-break targets. If a weekly target slips, it goes to the Risk & Issue Register with a recovery plan — not silently into next week.
Week | Dates | Theme | Targets (all must be true by Sunday night) | Owner | Evidence / where tracked | Status
W1 | 3–7 Sep | Foundation & mobilization | 1) Committee formed, cadence live. 2) ECG written confirmation + exhibitor manual on file (A1/A2). 3) Budget v1 with real quotes ratified; cost-share policy published. 4) Sponsorship deck out + wave-1 asks delivered. 5) ≥25 applications received by 7 Sep. | Project Director | Committee sheet; confirmation letter; Budget; Sponsors; applicant register
W2 | 8–14 Sep | Selection, design, invitations | 1) 10 + 2 companies selected & committed. 2) Assets 10/10 by 12 Sep; design signed off; print files at Karachi vendor. 3) All travel + hotel booked by 11 Sep. 4) A-list VIP invitations dispatched by 14 Sep. 5) 200-account B2B pool built; outreach started. 6) ≥2 sponsor commitments. | Workstream leads | Companies roster; print PO; tickets; Stakeholder DB; B2B sheet; Sponsors
W3 | 15–21 Sep | Rehearse, ship, build | 1) 2 rehearsal rounds done; reps pass lead-capture test. 2) Print proofs approved 15 Sep; delivered to venue 20 Sep. 3) ≥40 meetings booked; calendar published. 4) ≥8 VIP visits confirmed. 5) 3–5 MOUs sign-ready. 6) Pavilion built & signed off 21 Sep 18:00. | Project Director | Rehearsal scorecards; delivery note; B2B calendar; Gov-VIP; MOU tracker; setup photos
W4 | 22–28 Sep | Show & first follow-up | 1) Show KPIs: ≥150 leads, ≥40 meetings held, ≥5 MOUs signed, ≥8 VIP visits, daily coverage posted. 2) Every lead assigned an owner + follow-up date before leaving Karachi. 3) 48h thank-you wave complete by 27 Sep. 4) Dismantle clean; reusables stored for Lahore. | PD + BD + PMO | Lead Tracker; MOU tracker; Gov-VIP; daily reports
W5 | 29 Sep–5 Oct | Close-out | 1) 100% leads first-contacted. 2) Internal retro held; lessons logged. 3) Results press release out; Post-Event Report v1 drafted. 4) Sponsor fulfillment reports in production. | PMO / Follow-up | 30-60-90 sheet; Post-Event Report
Oct | 6–24 Oct | 30-day conversion | 1) Meetings from leads ≥20. 2) Proposals out ≥10. 3) MOU 30-day actions 100% done. 4) Sponsor reports delivered by 9 Oct. 5) 30-day review held 24 Oct with scorecard. | PMO / Follow-up | 30-60-90 sheet; Lead Tracker
Nov | 25 Oct–23 Nov | 60-day + Year-2 decision | 1) Pipeline value quantified. 2) 3 case studies published. 3) YEAR-2 DECISION: Lahore 29–31 Jan 2027 participation decided, booking confirmed with ECG, selection round 2 announced. | Project Director | 60-day scorecard; year-2 memo
Dec | 24 Nov–23 Dec | 90-day impact | 1) Impact report published (revenue, contracts, jobs, media reach). 2) Stakeholder debrief held (P@SHA/ECG, GB govt, sponsors). 3) Year-2 master workbook v1 ready. | Project Director | 90-day report; KPIs sheet

## Committee & Governance
GB PAVILION COMMITTEE, DECISION RIGHTS & OPERATING SYSTEM
Fill the Name column on 3–4 Sep (amber = unfilled). One person may hold at most two roles. Every role has a named backup for show days.
1. ROLES & RESPONSIBILITIES
Role | Name (fill in) | Contact (phone / email) | Responsibilities | Backup (show days)
Project Director (PD) | e.g. Nadia (initiative lead) |  | Overall accountability; chairs standups & steering; final sign-offs per matrix; VIP asks; year-2/3 strategy; represents pavilion to P@SHA/ECG/govt.
PMO & Follow-up Lead (deputy PD) |  |  | Owns this workbook (daily 18:00 update); dependencies & slippage; MOU drafting/tracking; daily show reports; runs the 30/60/90 machine.
PASHA / ECG Liaison |  |  | Single channel to Umair Nizam office, P@SHA secretariat, ECG ops; written confirmation; exhibitor manual; passes; exhibitor/delegate list; protocol coordination.
Companies & Selection Lead |  |  | Call for applications; selection panel secretary; commitment forms; asset collection; company readiness checklist; onboarding calls.
GBSHA Liaison (co-lead, companies) |  |  | Mobilization through GBSHA 40+ members; co-signs criteria; community trust; regrets → year-2 waitlist.
Sponsorship & Finance Lead |  |  | Budget & quotes; sponsorship packages, pipeline, closing; sponsor benefits fulfillment; expense tracking & variance; post-event sponsor reports.
Pavilion Design & Branding Lead |  |  | "Made in GB" identity; zone plan; pod template; ecosystem wall; print production & proofs; setup supervision; signing/photo corner.
Stakeholder & Protocol Lead |  |  | Stakeholder DB; verify officeholders; invitations & RSVPs; VIP slots, hosts, talking points, protocol kit; visit logging & thank-yous.
BD & B2B Lead |  |  | Target lists (company + central); outreach wave; meeting calendar; meeting kits; lead-capture system & training; daily lead sync; lead assignment.
Comms & Media Lead |  |  | Comms plan & calendar; announcement, spotlights, countdown; press kit & media relations; photo/video team; live coverage; post-event story pack.
Logistics & Travel Lead |  |  | Travel waves + weather fallback; hotel & vans; passes manifest; equipment kit; materials delivery & storage; emergency sheet; dismantle & back-haul.
2. DECISION & APPROVAL MATRIX
Decision | Decided by | Consulted | Rule | Turnaround
Spend > PKR 100,000 (single item) | PD + Sponsorship Lead | Steering | Two signatures; log in Budget Tracker | 24h
Spend ≤ PKR 100,000 (budgeted line) | Workstream lead | Sponsorship Lead | Within approved budget line | Same day
Company selection & replacements | Selection panel (Companies + GBSHA + PD) | Steering | Rubric scores; conflict-of-interest: scorers abstain on own company; PD casting vote | 24h
Design sign-off / print release | PD | Design Lead, Sponsorship (logos) | One sign-off, then FROZEN — changes after 12 Sep only for errors | 12h
Press release / public statements | PD + Comms Lead | PASHA Liaison | Nothing public before pavilion terms confirmed in writing | 12h
VIP asks & official letters | PD | Stakeholder Lead, Liaison | Asks per Gov-VIP sheet; letters on pavilion letterhead | 24h
MOU text approval | Signatory company + PD review | PMO | No MOU without named owner + 30-day action | 48h
Schedule changes at show | Floor Manager on duty | PD | Log at 18:30 debrief | Immediate
3. MEETING CADENCE & CHANNELS
Forum / channel | Who | When | Agenda / purpose | Owner
Daily standup (30 min) | All leads | 18:00, 3–21 Sep | Yesterday / today / blockers / risk review; workbook updated first | PD
Show-day briefing | Full delegation | 08:30, 22–24 Sep | Targets, VIP schedule, meeting slots, rota | PD
Show-day debrief + lead sync | Leads + reps | 18:30, 22–24 Sep | Leads exported & assigned; meetings logged; daily report drafted | BD + PMO
Steering review (45 min) | Committee | Sun 7 / 14 Sep + Go/No-Go 17 Sep | Weekly targets check; budget; escalations | PD
Committee WhatsApp | Committee | Always on | Speed; decisions confirmed in workbook | PMO
Companies WhatsApp | 10 companies + leads | Always on | Asset chase, logistics, show ops | Companies Lead
Shared drive | All | — | Assets, letters, quotes, MOUs, photos — single folder tree | PMO
This workbook | PMO edits; all read | Daily 18:00 | Single source of truth; verbal ≠ decided until logged here | PMO
4. ESCALATION PATH
Blocked >24h → raise at standup → PD decides or escalates to PASHA/ECG Liaison (external blockers) within 24h → still stuck: PD calls Umair Nizam office / P@SHA secretariat directly. Every escalation gets a row in the Risk & Issue Register. Principle: a fast imperfect decision beats a perfect one after the print deadline.

## Participating Companies
PARTICIPATING COMPANIES — SELECTION & READINESS
Target: 10 companies + 2 reserves representing the breadth of the GB ecosystem (software services, products/SaaS, e-commerce, edtech/tourismtech, freelancing collectives), with Gilgit/Skardu/Hunza spread and women-led inclusion. Sources to mobilize: GBSHA members (40+), SCO STP tenants (Gilgit/Skardu/Hunza), SCO-KIU incubatees, KIU KUBIC, e-Rozgaar alumni.
SELECTION RUBRIC (100 points) — published with the call on 4 Sep; scored by panel 7–8 Sep; conflict-of-interest rule applies
# | Criterion | Points | What good looks like
1 | GB-rooted | 15 | Registered/operating in GB or GB-founded team; real GB footprint (office, team, taxes)
2 | Product / service maturity | 20 | Live product or delivered client work; demo-able at a booth; references available
3 | Business readiness | 20 | Can sign and deliver new clients within 90 days; pricing exists; capacity to serve down-country/international work
4 | Team commitment | 15 | Two named reps for all 3 days + rehearsals; accepts cost-share policy and follow-up SLA
5 | Materials readiness | 10 | Logo, profile, 1-pager deliverable by 12 Sep (or realistic plan to get there)
6 | Ecosystem mix contribution | 10 | Adds sector/geographic diversity to the pavilion (incl. Skardu/Hunza, freelancing economy)
7 | Inclusion | 10 | Women-led/co-led or demonstrable women-in-team commitment (BEST4WEER alignment strengthens dev-org sponsorship case)
Application form fields: company, year founded, city, team size, services/products, 2 client references or portfolio links, revenue band (optional), reps proposed, why ITCN & what success looks like, assets readiness, cost-share acceptance. Regret letters offer priority consideration for ITCN Asia Lahore (29–31 Jan 2027).
ROSTER & READINESS CHECKLIST — one row per company; checkboxes Y/N; chase daily at standup
# | Company | Sector / offering | City | Primary contact | Phone | Email | Status | Rep 1 | Rep 2 | CNIC / passes | Profile 150w | Vector logo | One-pager | Demo plan | Booth needs (power/screen/gear) | Travel needs | B2B list (20) | Rehearsed ×2 | Notes
1 | Example: Karakoram Soft (replace) | Custom software / web | Gilgit | A. Khan | 03xx-xxxxxxx | name@company.pk | Applied | A. Khan | S. Ali | N | N | N | N | N | 1 screen, 2 laptops, 1 power strip | 2 pax ex-Gilgit | N | N | Example row — replace with a real applicant
Known candidate long-list from public sources — validate locally, this is NOT a shortlist: GBSHA member directory (primary source, 40+ firms); uConnect Technologies (Gilgit — software export, GilgitApp); Tech ALPHAlogix (Gilgit — web/design, BEST4WEER partner); Innovative Technologies GB (Gilgit — to verify); SCO STP tenants Gilgit/Skardu/Hunza; SCO-KIU incubation cohort startups. Status flow: Applied → Shortlisted → Selected → Confirmed (form signed). Dashboard counts Status = "Confirmed".

## Sponsors & Funding
SPONSORS & FUNDING — P3.2 VALUE PROPOSITION, CATEGORIES & PACKAGES
The pavilion space is free; the mission is not. Cash target PKR 1.85M + in-kind target PKR 1.2M = PKR 3.05M ≈ 60% of the recommended budget — the rest is covered by cost-share policy A6 and must-fund central lines. Execution lives in the Sponsor Pipeline sheet; this sheet defines what we sell and to whom. Tier pricing = recommendation (A10), ratify 4–5 Sep.
1. WHY SPONSOR THE GB PAVILION — THE VALUE PROPOSITION (use these lines in the deck)
Audience: a national-scale stage — the 28th ITCN Asia claims 850+ booths, 75,000+ trade visitors, 350+ international delegates, and ministerial/official traffic (organizer-claimed figures; the show is inaugurated at federal-minister level and runs under MoITT's Tech Destination Pakistan with SIFC endorsement).
Story scarcity: "the first Gilgit-Baltistan technology pavilion in Karachi" is a genuine first — media-friendly, CSR-friendly, and un-owned. A sponsor buys association with an emerging-ecosystem story no competitor has claimed (P@SHA's GB diagnostic: $15–18M sector, 100–120 active firms, 3,000–4,000 freelancers).
Three-year platform, not a one-off: the pavilion is committed for three years (A1 — being documented). Title and Gold partners are offered first right of renewal into ITCN Asia Lahore (29–31 Jan 2027) — a sponsor buys a platform position, not a single weekend.
Inclusion & impact angle: women-led GB companies, the BEST4WEER/Coalition-of-Employers lineage, and mountain-region digital inclusion give development organizations and CSR budgets a measurable, photographable outcome.
Concrete visibility: pavilion branding seen by walk-by traffic for 3 days, VIP visits with media in tow, MOU-ceremony moments, a countdown + live + results social campaign (≥40 posts), earned-media push to national tech press, and a post-event report delivered to P@SHA, ECG, GB government and sponsors.
Ecosystem access: sponsors get curated B2B access to 10 vetted GB companies and the delegation's government visitors — useful for banks (SME/digital acquisition), telecoms (GB market), cloud providers (developer adoption), and recruiters of northern talent.
2. SPONSOR CATEGORIES — WHY EACH WOULD SPONSOR (evidence-based; verify officeholders before outreach)
Category | Why they would sponsor (the specific hook) | Realistic ask | Evidence-based targets | Warm path
Banks & fintech | SME/digital-banking acquisition + CSR; HBL already title-sponsors the HBL-P@SHA ICT Awards (direct P@SHA relationship); HBL Microfinance Bank opened its GB regional HQ in Gilgit (2024, AKDN roots) — the GB story is literally their story | Gold/Silver cash; Supporting | HBL; HBL Microfinance Bank; Karakoram Cooperative Bank; BOP/NBP/Meezan (one is enough); JazzCash (fintech) | P@SHA secretariat (ICT Awards relationship); AKDN network for HBL MfB
Telecom operators | GB market leadership story (Zong ran its largest-ever GB 4G expansion 2024; partnered ITCN Islamabad 2023); SIM/data in-kind is trivially cheap for them and solves a real delegation need | Silver cash + SIMs/data in-kind | Zong; Jazz; PTCL/Ufone; SCO (GB operator — also Gold candidate) | Corporate marketing depts; SCO via GB IT Dept
Cloud & technology providers | Developer/startup adoption in an untapped region: 10 companies + 3–4k freelancers as new users; both run active PK programs (Huawei ICT Competition; Alibaba Cloud tech-partners the Bano Qabil AI Hackathon via Cognix) | Technology Partner: cloud credits, devices, training (in-kind ≥250k value) | Huawei; Alibaba Cloud (via Cognix Solutions); Microsoft/Google partner resellers; NTC (exhibits data-centre/cloud at ITCN) | Partner managers; NTC via ITCN exhibitor relations
Software houses (large P@SHA members) | Subcontracting/white-label bench in a lower-cost region + industry-citizenship visibility inside P@SHA | Silver/Supporting + B2B commitments (worth more than cash) | Systems Ltd, NetSol, Contour, 10Pearls-class firms (build named list via P@SHA) | P@SHA secretariat & ICT Awards sponsor circle
Development organizations | Measurable women-led/mountain-region inclusion outcome; Coalition-of-Employers lineage is their own program logic (BEST4WEER: AKF/AKRSP/Accelerate Prosperity) | Grants for women-led firms' participation; side-event funding | AKF / Accelerate Prosperity; AKRSP; UNDP (existing GB e-gov partner); AKFC/BEST4WEER | AKDN country offices; GB IT Dept for UNDP
Government-linked institutions | Their own mandate: P@SHA's GB diagnostic explicitly recommends subsidised expo access for GB firms; a GB pavilion is the mandate made visible | Grant/subsidy line (this year + recurring for years 2–3) | GB IT Department; PSEB; Ignite; TDAP (access, not cash); STZA (align messaging) | Secretary IT GB (Zameer Abbas); P@SHA intro to PSEB CEO
Corporates operating in GB | Local-license-to-operate CSR + brand warmth with GB audiences (Serena: 8 GB properties; Nestlé runs Clean Gilgit-Baltistan; NATCO is GB's own carrier) | Supporting cash / in-kind (souvenirs, GB-side logistics) | Serena Hotels; Nestlé Pakistan; NATCO; HBL MfB (also banks row) | GB govt & tourism networks; GBSHA members
Airlines & travel | Regional-development PR at near-zero marginal cost (seats fly anyway) | Travel Partner: fare discounts/waivers (in-kind) | PIA (only GIL operator); Airblue (Skardu jets); travel agencies | PIA regional sales office
Hospitality (Karachi) | 13 rooms × 6 nights of guaranteed group business + visibility to a national campaign | Hospitality Partner: room-rate discount/upgrade (in-kind) | Regent Plaza (~nearest), Mövenpick, Avari, PC — TDAP-endorsed delegate hotels near Expo Centre | Direct group-sales negotiation
Universities & academia | Talent-pipeline story; recruiting visibility to GB student market | Supporting (small cash / venue for prep events) | KIU (KUBIC incubator), University of Baltistan; down-country CS departments | KIU leadership via GBSHA
International development partners | Digital-economy inclusion programming; a ready-made pilot region | Side-event funding; year-2 program partnership (not fast cash) | UNDP; World Bank digital team; GIZ; DCO (named on ITCN Karachi page) | Via GB IT Dept / MoITT channels — long-cycle, start now for year 2
Investment ecosystem / VCs | Deal-flow access to an unscouted region — cheap optionality for funds | Investor-breakfast host (ENH); Supporting; mostly TIME not cash | Active PK funds & angel networks (verify current funds by 8 Sep; Accelerate Prosperity bridges) | BD Lead direct + P@SHA intros
Digital platforms & marketplaces | Seller/partner acquisition (e-commerce enablement for GB firms + freelancers) | Supporting cash / platform credits | Daraz-class marketplaces; payment gateways; freelancing platforms' PK reps (verify current programs) | Corporate partnership teams
Media partners | Content: a first-of-its-kind story with photos, founders, mountains — coverage barter costs them nothing | Media Partner: coverage commitment + logo swap (barter) | ProPakistani (covered the GB diagnostic — warmest), TechJuice, Pamir Times; BR/Dawn for business desk | Comms Lead press kit 15 Sep
3. SPONSORSHIP PACKAGES — TIERS & BENEFITS (the benefits matrix IS the negotiation boundary; exceptions need PD sign-off)
Tier | Value (PKR) | Slots | Pavilion & branding visibility | Digital & social visibility | Speaking / ceremony | VIP, B2B & partnership access | Post-event visibility | Deadline & notes
TITLE / STRATEGIC PARTNER | 1,500,000 | 1 | Exclusive naming: "GB Pavilion powered by X" on fascia + backdrop + ecosystem wall strip; logo on every printed item; premium placement | Logo on all ≥40 campaign posts; named in announcement + results releases; 2 dedicated posts; tag rights | Speaking moment at the Day-2 MOU ceremony; quote in press release; option to host GB Night (ENH scenario) | 4 VIP passes; hosted tour for their leadership; first-priority B2B slots with all 10 companies; MOU option with the pavilion/GBSHA; first right of renewal for Lahore Jan 2027 | Cover credit on post-event report; results-release first mention; wrap-video credit | Logos by 12 Sep for print. Cap: counts ≤35% of total raise in planning (Risk R22)
GOLD PARTNER | 750,000 | 2 | Logo on backdrop + screens + sponsor board; large placement | Logo on all posts; named in releases; 1 dedicated post | Named at MOU ceremony; may witness a signing | 2 VIP passes; guided tour; priority B2B slots; renewal option Lahore | Report section credit; results-release mention | Logos by 12 Sep for print
SILVER PARTNER | 300,000 | 4 | Logo on sponsor board + screens | Logo block on campaign posts; thank-you post | — | 1 pass; B2B slots on request | Report credit | Logos by 12 Sep for print; after that digital-only
SUPPORTING PARTNER | 100,000 | 6 | Name on sponsor board | Thank-you post (grouped) | — | Invitation to Day-2 networking | Report listing | Open through 16 Sep; digital + report benefits
TRAVEL PARTNER | in-kind (≥300k value) | 1–2 | Logo on sponsor board + "delegation flies with X" journey content | Journey-day posts (KKH/airport — highest-emotion content of the campaign) | — | Invitation to Day-2 networking | Report credit | Fare waivers/discounts; commit by 10 Sep (bookings close 11 Sep)
HOSPITALITY PARTNER | in-kind (≥300k value) | 1 | Logo on sponsor board; "official hotel" designation | Check-in/delegation content tagged; thank-you post | — | Delegation dinner hosted on property (optional) | Report credit | Room block discount/upgrade; commit by 10 Sep
TECHNOLOGY PARTNER | in-kind (≥250k value) | 1–2 | Logo on screens + "powered by" line on demo wall | Dedicated post on the credits/devices/connectivity provided | Optional 15-min tech talk at the pavilion | B2B with all 10 companies (their adoption pipeline); MOU option for developer program | Report credit + case study option | Cloud credits / devices / connectivity for the 10 companies; commit by 15 Sep
MEDIA PARTNER | barter | 2–3 | "Media partner" on sponsor board | Logo swap; content co-publishing | Interview access to founders + VIPs | Press desk access; first-interview rights Day 1 | Co-branded results feature | Coverage commitment agreed in writing by 15 Sep
IN-KIND PARTNER (general) | value-based (≥100k) | open | Recognition matched to equivalent cash tier | Thank-you post | — | Per equivalent tier | Report listing | Print/AV/design/logistics services; value agreed in writing
4. REVENUE PLAN & HONESTY MATH (live)
Cash target | 1850000 | Realistic mix: 1 Title + 1 Gold + 3 Silver + 4–5 Supporting at ~50% close rate on a 25+ target pipeline — full sellout would be ≈3.55M; do not plan on it
In-kind target (assigned value) | 1200000 | Fares + hotel + SIMs/data + screens/AV + print discount + cloud credits + ECG extras
Total sponsorship target | 3050000 | ≈60% of the recommended budget (Budget Tracker C5); balance = cost-share policy A6 + must-fund central lines
Pipeline potential (live) | 8550000 | Rule of thumb: potential must stay ≥2.5× the cash target
Weighted pipeline (live) | 2565000 | Σ (potential × probability) — the honest forecast; keep ≥ total target from 8 Sep onward
Committed — cash (live) | 0 | Letters on file only
Committed — in-kind (live) | 0 | Agreed value in writing
Gap vs target (live) | 3050000 | Escalate if > 40% of target on 15 Sep (Risk R19)
Guardrails: (1) benefits outside this matrix need PD sign-off — no exclusivity below Title, no agenda/editorial control over GB content at any tier, no competitor-blocking promises; (2) a verbal commitment converts to a signed letter within 48h or drops back to Negotiation; (3) logos by 12 Sep 18:00 for print — later commitments get screens/social/report benefits only (say this in every proposal from day one); (4) every committed sponsor gets a fulfillment checklist and the 9 Oct post-event report. Tier pricing and probability weights are planning assumptions — ratify 4–5 Sep (A10/A13).

## Sponsor Pipeline
SPONSOR PIPELINE — P3.3 TARGET DATABASE & SALES PIPELINE (ONE TRACKER, NO DOUBLE ENTRY)
Stages: Prospect → Contacted → Meeting → Proposal → Negotiation → Verbal Commitment → Confirmed → Fulfilled (Declined closes a row honestly). A stage moves right only with evidence; "Confirmed" requires a signed letter; a Verbal not converted to written within 48h drops back to Negotiation. Probability weights are planning assumptions (A13) — recalibrate at the 8 & 15 Sep reviews. No invented contact names: role-level contacts until a real name is confirmed.
PIPELINE FUNNEL (live)
Prospect | Contacted | Meeting | Proposal | Negot. | Verbal | Confirmed | Fulfilled | Declined |  | Potential (PKR) | Weighted (PKR) | Committed cash | Committed in-kind | Target (cash+in-kind) | Gap vs target
24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8550000 | 2565000 | 0 | 0 | 3050000 | 3050000
WEEKLY SPONSORSHIP TARGETS (cumulative; Actual row is live where formulas allow)
Week | Dates | Identified | Contacted | Meetings held | Proposals sent | Commitments | Cash committed | In-kind committed | Gap remaining | Status / notes
W1 | 3–7 Sep | 25+ | 15 | 2 | 8 | 2 (≥1 govt LOI) | ≥ 500,000 | ≥ 250,000 | ≤ 2,300,000 | Wave-1 asks out 5 Sep; ECG bundle in confirmation thread
W2 | 8–14 Sep | 30 | 25 | 10 | 15 | 5 | ≥ 1,200,000 | ≥ 600,000 | ≤ 1,250,000 | Meetings 8–11; logo cutoff notice 11 Sep; kill <20% prob targets 12 Sep
W3 | 15–18 Sep | 30 | 28 | 14 | 18 | 8 | ≥ 1,850,000 | ≥ 1,200,000 | 0 (or decision) | Close & convert verbals; funding-position review 15 Sep
By 18 Sep | — | — | — | — | — | — | — | — | Gap decision | Funding position memo published; contingency active (R19); unresolved big asks → PD/ECG channel in Karachi 20–21 Sep
Actual (live) |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 3050000 | Auto — do not type over
Organization | Category | Prio | Strategic fit / hook | Warm path / intro via | Contact (role or verified name) | Contact details | Cash / In-kind | Potential (PKR) | Prob % | Weighted (PKR) | Owner | Stage | First approach | Proposal sent | Meeting date | Next action | Committed (PKR) | Deliverables promised | Follow-up due | Close by | Notes
GB IT Department (Govt of GB) | Government | P1 | Its own mandate made visible: e-Rozgaar, Google certs, co-working; P@SHA diagnostic recommends subsidised expo access; year-2 recurring line built into the ask | Secretary IT direct; GB CM office | Zameer Abbas, Secretary IT (office) | via gbit.gov.pk channel | Cash | 750000 | 40% | 300000 | PD | Prospect |  |  |  | Send letter + deck 5 Sep; call same day |  |  |  | 2026-09-12 | LOI acceptable by 12 Sep if funds need process (R18)
PSEB | Government | P1 | Diagnostic-aligned mandate; runs its own ITCN pavilions; frame as pilot of a recurring GB expo-subsidy line | P@SHA secretariat intro | CEO office (Faisal Jeddy — verify) | via P@SHA | Cash | 750000 | 30% | 225000 | Sponsorship Lead | Prospect |  |  |  | Send 5 Sep citing diagnostic; meeting 8–10 Sep |  |  |  | 2026-09-15 | Years 2–3 framing matters more than this year
SCO | Telecom / Govt | P1 | The pavilion showcases SCO's own ecosystem investments (STPs Gilgit/Skardu/Hunza, KIU incubation, freelancing hubs) | GB IT Dept; STP management | DG office |  | Cash | 750000 | 35% | 262500 | Sponsorship Lead | Prospect |  |  |  | Letter 5 Sep; meeting 9–11 Sep |  |  |  | 2026-09-12 | Fallback: Gold + connectivity in-kind
AKF / Accelerate Prosperity | Development | P1 | BEST4WEER / Coalition-of-Employers lineage; women-led GB companies at a national expo = their program outcome, photographable | AKDN country office; BEST4WEER team | Program leadership (office) |  | Cash | 500000 | 35% | 175000 | PD | Prospect |  |  |  | WEE-framed concept note 5 Sep |  |  |  | 2026-09-15 | May arrive as earmarked grant (women-led firms travel)
HBL | Bank | P1 | Title sponsor of HBL-P@SHA ICT Awards 2025 — proven budget for P@SHA-adjacent properties; SME/digital acquisition angle | P@SHA secretariat (ICT Awards circle) | Corporate sponsorship (via P@SHA) |  | Cash | 750000 | 25% | 187500 | PD | Prospect |  |  |  | Warm-intro request 6 Sep; deck 8 Sep |  |  |  | 2026-09-15 | Gold ask; probe Title appetite
HBL Microfinance Bank | Bank | P1 | GB regional HQ inaugurated in Gilgit 2024; AKDN/AKRSP roots since 1982 — the GB story is their story | AKDN network; Gilgit RHQ | Regional leadership (office) |  | Cash | 300000 | 35% | 105000 | Sponsorship Lead | Prospect |  |  |  | Letter 6 Sep |  |  |  | 2026-09-15 | Silver + GB-side visibility
Zong (CMPak) | Telecom | P1 | Largest-ever GB 4G expansion (2024); partnered ITCN Islamabad 2023 — event-category precedent | Corporate marketing dept | Corporate marketing (office) |  | Cash | 300000 | 30% | 90000 | Sponsorship Lead | Prospect |  |  |  | Deck 7 Sep + SIMs/data in-kind ask |  |  |  | 2026-09-15 | Silver + Technology/telecom in-kind bundle
Karakoram Cooperative Bank | GB bank | P2 | e-Rozgaar 5% loan partner; GB-identity brand in front of a national audience | Head office Gilgit; GB IT Dept | Head office |  | Cash | 300000 | 30% | 90000 | GBSHA Liaison | Prospect |  |  |  | Letter 7 Sep |  |  |  | 2026-09-15 | Silver or community-patron profile
GB diaspora patrons (target ×5) | Community | P2 | Pride + visibility; low-friction 100k Supporting tier for GB-origin business owners | GBSHA networks | via GBSHA |  | Cash | 500000 | 40% | 200000 | GBSHA Liaison | Prospect |  |  |  | Mini-deck 6 Sep; close in batches |  |  |  | 2026-09-16 | 5 × PKR 100k Supporting
Serena Hotels | GB corporate | P2 | 8 properties in/around GB — the region's hospitality brand; souvenirs/GB-side events in-kind also valuable | GB tourism/govt network | Marketing / CSR (office) |  | Cash | 200000 | 25% | 50000 | GBSHA Liaison | Prospect |  |  |  | Letter 7 Sep |  |  |  | 2026-09-16 | Supporting + in-kind options (no KHI property)
Nestlé Pakistan | Corporate CSR | P2 | Runs "Clean Gilgit-Baltistan" CSR — proven GB budget; digital-inclusion adjacency | Corporate affairs | Corporate affairs (office) |  | Cash | 300000 | 20% | 60000 | Sponsorship Lead | Prospect |  |  |  | Letter 8 Sep |  |  |  | 2026-09-16 | CSR framing, not tech framing
Ignite | Government | P2 | National startup mandate; GB inclusion story it can claim in reporting | P@SHA intro | CEO office (Bilal Abbasi — verify) |  | Cash | 300000 | 25% | 75000 | Sponsorship Lead | Prospect |  |  |  | Letter 8 Sep |  |  |  | 2026-09-16 | Also ask: NIC-style program for GB (non-cash win)
PTCL / Ufone Group | Telecom | P2 | National digital-Pakistan positioning; GITEX-scale event spender | Corporate affairs | Corporate affairs (office) |  | Cash | 300000 | 20% | 60000 | Sponsorship Lead | Prospect |  |  |  | Deck 8 Sep |  |  |  | 2026-09-16
Jazz / JazzCash | Telecom / fintech | P2 | S-Paisa × SCO integration precedent; GB freelancer-payments angle | Corporate affairs | Corporate affairs (office) |  | Cash | 300000 | 20% | 60000 | Sponsorship Lead | Prospect |  |  |  | Deck 8 Sep |  |  |  | 2026-09-16
UNDP Pakistan | Development | P2 | Existing e-governance partnership with GB IT Dept; inclusive digital economy agenda | GB IT Dept partnership channel | Digital team (office) |  | Cash | 300000 | 20% | 60000 | PD | Prospect |  |  |  | Concept note 8 Sep |  |  |  | 2026-09-16 | Likely year-2 program money — start now (R18)
BOP / NBP / Meezan (one needed) | Bank | P3 | SME & digital-banking narratives; expo sponsorship precedent at national events | SME / marketing departments | Marketing (office) |  | Cash | 300000 | 15% | 45000 | Sponsorship Lead | Prospect |  |  |  | Parallel letters 9 Sep |  |  |  | 2026-09-16 | First responder wins the Silver slot
Huawei | Technology | P3 | Active PK talent spend (Huawei ICT Competition); GB = untouched developer market | Partner/education managers | Partner manager (office) |  | In-kind | 250000 | 20% | 50000 | BD Lead | Prospect |  |  |  | Technology-partner note 8 Sep |  |  |  | 2026-09-15 | Devices / training / cloud credits for 10 companies
Alibaba Cloud (via Cognix Solutions) | Technology | P3 | Tech-partners Bano Qabil AI Hackathon 2026 via Cognix; credits = cheap adoption in a new region | Cognix Solutions (authorized partner) | Partner desk (office) |  | In-kind | 250000 | 20% | 50000 | BD Lead | Prospect |  |  |  | Note via Cognix 8 Sep |  |  |  | 2026-09-15 | Cloud credits for the 10 companies
NTC | Technology / Govt | P3 | Exhibits data-centre/cloud at ITCN; govt-tech alignment with GB e-governance | ITCN exhibitor relations | Business development (office) |  | In-kind | 150000 | 20% | 30000 | PASHA/ECG Liaison | Prospect |  |  |  | Pre-note 9 Sep + on-site meeting |  |  |  | 2026-09-20 | Hosting/connectivity for GB e-gov demos
PIA | Travel | P1 | Only Gilgit operator; regional-development PR at near-zero marginal cost | Regional sales office | Regional sales (office) |  | In-kind | 300000 | 30% | 90000 | Logistics Lead | Prospect |  |  |  | Fare-discount letter 5 Sep; chase daily |  |  |  | 2026-09-10 | HARD gate: bookings close 11 Sep
Hotel partner (Regent Plaza / Mövenpick class) | Hospitality | P1 | 78+ guaranteed room-nights + "official hotel" designation in a national campaign; TDAP-endorsed delegate hotels near Expo Centre | Group sales direct | Group sales desk |  | In-kind | 300000 | 40% | 120000 | Logistics Lead | Prospect |  |  |  | Group-rate negotiation 5–8 Sep |  |  |  | 2026-09-10 | Rate discount/upgrades as in-kind value
Karachi print vendor | In-kind | P2 | Full pavilion print job now + repeat business for Lahore Jan 2027 | Direct (vendor selection 12 Sep) | Sales desk |  | In-kind | 100000 | 40% | 40000 | Design Lead | Prospect |  |  |  | Discount ask inside the quote round 10 Sep |  |  |  | 2026-09-12 | 10–15% discount booked as in-kind
ECG / ITCN Asia | Organizer | P1 | Wants its regional-inclusion showcase to succeed; controls passes, hall branding, delegate lists, stage time | Umair Nizam office (SVC P@SHA / VP & Event Director, ECG); ECG President/CEO office is the top signatory | Event management (office) | info@itcnasia.com; +92-21-38709970 | In-kind | 200000 | 50% | 100000 | PASHA/ECG Liaison | Prospect |  |  |  | Bundle with written confirmation 3–5 Sep |  |  |  | 2026-09-08 | Extra passes, branding spots, delegate-list access, stage slot
Media partners (ProPakistani / TechJuice / Pamir Times) | Media | P2 | A first-of-its-kind story with founders and mountains — barter coverage costs them nothing; ProPakistani already covered the GB diagnostic | Comms press kit | Editorial desks |  | In-kind | 100000 | 40% | 40000 | Comms Lead | Prospect |  |  |  | Media-partner offer with press kit 15 Sep |  |  |  | 2026-09-18 | Coverage commitment in writing
Operating rules: every row always has a Next action + Close-by date; follow-up within 48h of any meeting; a target silent after 3 touches → Declined (no zombie prospects). Cross-checks: Committed values feed Budget Tracker C6 and the Dashboard automatically. Sponsorship risks live in the Risk & Issue Register (R17–R22).

## Sponsorship Daily Plan
SPONSORSHIP DAILY ACTION PLAN — 3–18 SEP (P3.3)
The sponsorship track of the master Daily Action Plan, at execution grain. Rhythm: mornings = outreach & meetings; standup 18:00 = pipeline stages updated, weighted total read out against target (PKR 3.05M). P1 = do or the drive slips; P2 = same-day important.
Date | Day | Prio | Action | Owner | Expected outcome | Deadline | Dependency | KPI | Done?
2026-09-03 | Thu | P1 | Draft budget scenarios (MVB/REC/ENH) and send all quote requests (travel, hotel, print, AV, vans) | Sponsorship + Logistics | Cost model queued for 6 Sep ratification | 18:00 | Master kickoff (1.1) | Quote requests 100% out
|  | P1 | Draft value proposition + tier sheet + 2-page deck skeleton | Sponsorship Lead | Sellable proposition v0.9 | 18:00 | Budget v0 | Deck draft exists
|  | P1 | Build pipeline: ≥25 targets loaded with hooks, owners, close-by dates (Sponsor Pipeline sheet) | Sponsorship Lead + PD | Every target owned; wave-1 four confirmed | 18:00 | Tier sheet | 25+ rows, 0 unowned
|  | P2 | Request P@SHA warm-intro list (HBL/ICT-Awards circle, PSEB, Ignite) and ECG in-kind bundle framing | PASHA/ECG Liaison | Intro channels identified | 18:00 | Written-confirmation thread (1.2) | Intro requests sent
2026-09-04 | Fri | P1 | Committee ratifies tiers, targets (cash 1.85M / in-kind 1.2M) and probability discipline | Steering Committee | Pricing & targets frozen | 12:00 | Tier sheet | Minuted decision
|  | P1 | Finalize deck (PDF) + 1-page letter template + per-target personalization notes | Sponsorship + Comms | Send-ready pack | 18:00 | Ratified tiers | Pack approved by PD
|  | P1 | Personalize wave-1 letters: GB IT Dept, PSEB (cite diagnostic), SCO, AKF/Accelerate Prosperity | Sponsorship Lead | 4 letters ready to send | 18:00 | Pack | 4 letters staged
|  | P2 | Diaspora patron mini-deck (100k Supporting tier) drafted for GBSHA networks | GBSHA Liaison | Low-friction ask ready | 18:00 | Ratified tiers | Mini-deck ready
2026-09-05 | Sat | P1 | SEND wave-1 asks (4) + same-day phone call to each office; log stages to Contacted | Sponsorship + PD | Wave-1 in play | 12:00 | Letters | 4 sent + 4 calls logged
|  | P1 | PIA fare-discount letter + hotel group-rate negotiation opened (in-kind track) | Logistics Lead | Travel/hotel in-kind in motion | 18:00 | Quote round | 2 in-kind asks live
|  | P1 | ECG in-kind bundle asked inside the confirmation thread (passes, branding spots, delegate list, stage slot) | PASHA/ECG Liaison | Organizer in-kind scoped | 18:00 | 1.2 thread | Bundle requested
|  | P2 | Media-partner concept noted for 15 Sep press kit (ProPakistani warmest) | Comms Lead | Barter path planned | 18:00 | — | Noted in calendar
2026-09-06 | Sun | P1 | Quotes in → ratify RECOMMENDED budget; C5 goes live as the sponsorship denominator | Steering Committee | Real number to raise against | 18:00 | Quote returns | Budget ratified (A5 closed)
|  | P1 | HBL + HBL Microfinance warm intros requested via P@SHA / AKDN channels | PD | Bank track opened warm | 18:00 | Intro list (3 Sep) | 2 intro requests confirmed
|  | P2 | Diaspora patron drive soft-launch through GBSHA groups | GBSHA Liaison | First patron conversations | 18:00 | Mini-deck | ≥5 conversations started
2026-09-07 | Mon | P1 | Chase wave-1: responses logged; meetings booked into 8–11 Sep | Sponsorship Lead | Wave-1 meetings on calendar | 18:00 | Wave-1 sent | ≥3 meetings booked
|  | P1 | Wave-2 batch 1 out: Zong, KCBL, Serena | Sponsorship + GBSHA | Commercial + GB corporate tracks live | 18:00 | Deck | 3 asks delivered
|  | P2 | Weekly review vs W1 targets: 15 contacted / 2 commitments trajectory; recalibrate probabilities | PD | Honest funnel snapshot | 18:30 | Pipeline updated | W1 row scored
2026-09-08 | Tue | P1 | Wave-1 meetings begin (target 2 today); every meeting ends with a specific tier ask + LOI option | PD + Sponsorship | First verbal signals | 18:00 | Bookings | 2 meetings held
|  | P1 | Wave-2 batch 2 out: Nestlé, Ignite, PTCL/Ufone, Jazz, UNDP | Sponsorship Lead | Full cash pipeline in motion | 18:00 | Deck | 5 asks delivered
|  | P2 | Technology-partner notes out: Huawei, Alibaba Cloud (via Cognix) — cloud credits/devices for the 10 companies | BD Lead | In-kind tech track live | 18:00 | Deck | 2 notes sent
2026-09-09 | Wed | P1 | Meetings (2–3); govt targets pushed explicitly for LOI-by-12-Sep | PD + Sponsorship | Govt LOIs in writing queue | 18:00 | Meetings held | ≥1 LOI promised
|  | P2 | Bank batch out: BOP/NBP/Meezan parallel letters (first responder wins Silver) | Sponsorship Lead | Bank category widened | 18:00 | Deck | 3 letters out
|  | P2 | NTC pre-note (technology in-kind; on-site meeting at ITCN offered) | PASHA/ECG Liaison | Organizer-adjacent target engaged | 18:00 | — | Note sent
2026-09-10 | Thu | P1 | Negotiations: convert strongest wave-1/2 conversations; FIRST CONFIRMED commitment targeted today | PD | Momentum proof for other targets | 18:00 | Meetings 8–9 Sep | ≥1 Confirmed (letter)
|  | P1 | PIA + hotel in-kind DECISION DEADLINE — bookings happen tomorrow regardless | Logistics Lead | Travel costs settled either way | 18:00 | Asks 5 Sep | In-kind status known
|  | P2 | Print vendor discount ask inside quote round (in-kind) | Design Lead | Print in-kind scoped | 18:00 | Vendor shortlist | Ask made
2026-09-11 | Fri | P1 | Logo-deadline notice to ALL warm targets: vector logos by 12 Sep 18:00 or digital-only benefits | Sponsorship Lead | Print inclusion protected | 12:00 | Design freeze 12 Sep | 100% warm targets noticed
|  | P1 | Close diaspora patrons batch 1 (target 2–3 × 100k) | GBSHA Liaison | Supporting tier filling | 18:00 | Soft launch 6 Sep | ≥2 patron commitments
|  | P2 | Verbal commitments → letters within 48h rule enforced; letters drafted same day | Sponsorship Lead | No decaying verbals | 18:00 | Any verbal | 0 verbals older than 48h
2026-09-12 | Sat | P1 | LOGO CUTOFF 18:00 — confirmed sponsors' vectors to Design for print files | Sponsorship → Design | Sponsors in the print pack | 18:00 | Design freeze | All confirmed logos delivered
|  | P1 | Pipeline surgery: recalibrate probabilities; park/kill <20% targets; refocus on closables | PD + Sponsorship | Effort concentrated where it can land | 18:30 | Funnel review | Weighted ≥ target or gap flagged
|  | P2 | Commitment letters + fulfillment checklists opened per confirmed sponsor | Sponsorship Lead | Deliverables promised = deliverables tracked | 18:00 | Confirmations | Checklist per sponsor
2026-09-13 | Sun | P2 | Second push on Silver/Supporting (post-print benefits: screens, social, report) to undecided targets | Sponsorship Lead | Late-tier revenue without print dependency | 18:00 | Logo cutoff passed | ≥5 follow-ups sent
|  | P2 | Sponsor mentions drafted into 15 Sep press release + social calendar | Comms Lead | Fulfillment begins in public | 18:00 | Confirmed list | Release draft updated
2026-09-14 | Mon | P1 | Close pending Golds: PD calls on every stuck P1 target; escalation via P@SHA/ECG where useful | PD | Gold slots resolved either way | 18:00 | Pipeline review 12 Sep | Gold slots decided
|  | P2 | W2 review vs targets (25 contacted / 5 commitments / cash ≥1.2M); gap math updated | PD | Honest W2 scorecard | 18:30 | Pipeline current | W2 row scored
2026-09-15 | Tue | P1 | FUNDING-POSITION REVIEW at steering: committed vs 3.05M; if coverage <40% → trigger cost-share posture per A6 (companies briefed same evening) | Steering Committee | No surprise on 18 Sep | 18:30 | Pipeline current | Decision minuted (R19)
|  | P2 | Media-partner offers out with press kit (ProPakistani, TechJuice, Pamir Times) | Comms Lead | Barter coverage locked | 18:00 | Press kit ready | ≥2 media-partner agreements in motion
|  | P2 | Technology-partner closes (Huawei/Alibaba/NTC): value agreed in writing or parked for on-site | BD Lead | Tech in-kind resolved | 18:00 | Notes 8–9 Sep | Status decided per target
2026-09-16 | Wed | P1 | Close remaining Silver/Supporting; every in-kind confirmation documented with an agreed PKR value | Sponsorship Lead | In-kind counted honestly | 18:00 | — | All in-kind valued in writing
|  | P2 | Sponsor guest passes + VIP invitations list to Stakeholder Lead (fulfillment) | Sponsorship Lead | Benefits delivery scheduled | 18:00 | Confirmed list | Passes list delivered
2026-09-17 | Thu | P1 | Funding-position memo drafted for Go/No-Go: committed cash, in-kind, gap, contingency posture | Sponsorship Lead | Go/No-Go input ready | 12:00 | 15 Sep review | Memo at steering
|  | P2 | Show-day sponsor deliverables mapped to owners (logos on screens, mentions, tours, ceremony rolls) | Sponsorship + Comms | Fulfillment runs itself on show days | 18:00 | Checklists | Owner per deliverable
2026-09-18 | Fri | P1 | PUBLISH FINAL FUNDING POSITION: cash, in-kind, gap, active contingency; thank-you notes to every committed sponsor | PD + Sponsorship | Clear money picture before wheels-up | 12:00 | Memo 17 Sep | Position published to committee + P@SHA
|  | P1 | Unresolved high-value asks (PSEB/SCO/HBL class) → escalate for PD + ECG-channel meetings in Karachi 20–21 Sep | PD + Liaison | Big fish get a second window | 18:00 | Position memo | Karachi meeting list set
|  | P2 | Pipeline handover to fulfillment mode; T/U columns re-dated for post-event follow-ups | Sponsorship Lead | Nothing dropped in transit | 18:00 | — | All rows have next action
Links: master-plan context in Daily Action Plan Sep 3-18; money math in Budget Tracker; what we sell in Sponsors & Funding; who we sell to in Sponsor Pipeline; sponsorship risks R17–R22 in the Risk & Issue Register.

## Stakeholder Database
STAKEHOLDER DATABASE — WHO MUST KNOW, VISIT, OR CHAMPION THE PAVILION
Priority A = personal invitation + confirmed slot + host; B = invitation + follow-up; C = announcement reach. Verify every officeholder before inviting (A11) — several changed in 2026. Categories: Federal, GB Govt, P@SHA/Industry, Investor, International/Dev, Diplomatic, Media, Academia.
Name (verify!) | Title / organization | Category | Prio | Relationship owner | Invite sent | RSVP | Visited | Follow-up owner | Notes / hook
Shaza Fatima Khawaja | Federal Minister for IT & Telecom (as of Sep 2026 — verify) | Federal | A | PASHA/ECG Liaison |  |  |  |  | Likely at official opening — request pavilion stop on her route
Zarrar Hasham Khan | Secretary MoITT (verify) | Federal | A | PASHA/ECG Liaison |  |  |  |  | Policy ask: GB inclusion in national IT programs
Faisal Jeddy | CEO PSEB (apptd Jan 2026 — verify) | Federal | A | Sponsorship Lead |  |  |  |  | Ask: recurring expo subsidy for GB firms (cite P@SHA diagnostic)
Muhammad Bilal Abbasi | CEO Ignite (apptd Jun 2026 — verify) | Federal | A | Sponsorship Lead |  |  |  |  | Ask: NIC/incubation footprint for GB
SIFC secretariat (tech desk) | Special Investment Facilitation Council | Federal | B | PASHA/ECG Liaison |  |  |  |  | GB in investment-facilitation narrative
TDAP chief executive / IT div | Trade Development Authority | Federal | B | PASHA/ECG Liaison |  |  |  |  | GITEX-style slots for GB firms; intl delegate intros
NITB leadership | National IT Board (ITCN partner) | Federal | C | Liaison |  |  |  |  | e-governance angle with GB IT Dept
Amjad Hussain (Azar) | Chief Minister GB (elected Jun 2026) | GB Govt | A | PD |  |  |  |  | Patronage; year-2 co-funding; possibly opens pavilion Day 1
GB Minister for IT (name TBC) | Elected cabinet Jul 2026 — portfolio holder to confirm | GB Govt | A | Stakeholder Lead |  |  |  |  | Confirm name via Secretary IT by 10 Sep
Zameer Abbas | Secretary IT, Govt of GB | GB Govt | A | PD |  |  |  |  | Channel to CM office + co-funding; invite as delegation patron
Arshad Majeed Mohmand | Chief Secretary GB (verify) | GB Govt | B | PD
Sajjad Mustafa Syed | Chairman P@SHA (reinstated Aug 2026) | P@SHA / Industry | A | PD |  |  |  |  | Institutional support; invite to MOU ceremony
Muhammad Umair Nizam | SVC P@SHA / VP ECG — pavilion patron | P@SHA / Industry | A | PD |  |  |  |  | Host him for a full pavilion tour + photo; year-2/3 frame
P@SHA Secretary General | P@SHA secretariat | P@SHA / Industry | B | Liaison |  |  |  |  | Operational coordination
GBSHA leadership | GB Software Houses Association | P@SHA / Industry | A | GBSHA Liaison |  |  |  |  | Co-hosts; on-stage presence
CEOs of top P@SHA member firms | Systems, NetSol, Arbisoft, 10Pearls etc. (build named list by 10 Sep) | P@SHA / Industry | B | BD Lead |  |  |  |  | Subcontracting/white-label pipelines for GB firms
Pakistani VC funds | e.g. Sarmayacar, Zayn VC, i2i Ventures, 47 Ventures (verify active funds; build named list by 10 Sep) | Investor | A | BD Lead |  |  |  |  | Investor walk-through slot Day 2
Angel networks / accelerators | Accelerate Prosperity, NIC alumni networks, Katalyst Labs (verify) | Investor | B | BD Lead |  |  |  |  | GB startup pipeline story
International delegates program | 350+ intl delegates via ECG/TDAP (organizer-claimed) | International | A | PASHA/ECG Liaison |  |  |  |  | Request delegate list + matchmaking slots (6.3)
AKF / AKDN country leadership | Aga Khan Foundation Pakistan | International / Dev | B | PD |  |  |  |  | BEST4WEER & Hunza STP continuity; women-led firms story
AKRSP leadership | Aga Khan Rural Support Programme | International / Dev | C | PD |  |  |  |  | GB development narrative
UNDP Pakistan digital team | UNDP | International / Dev | B | Stakeholder Lead |  |  |  |  | e-governance partner of GB IT Dept
World Bank digital-economy team | World Bank Pakistan | International / Dev | C | Stakeholder Lead |  |  |  |  | Future GB digital programs
Embassy trade counsellors | Via TDAP/ECG diplomatic invites (China, UAE, KSA, UK, US priority) | Diplomatic | B | Liaison |  |  |  |  | Export-market connects; pavilion stop on diplomatic tours
ProPakistani | Tech media (covered GB diagnostic Nov 2025) | Media | A | Comms Lead |  |  |  |  | Offer exclusive: first GB pavilion in Karachi
TechJuice | Tech media | Media | B | Comms Lead
Business Recorder / Dawn tech desk | Business media | Media | B | Comms Lead
APP / Radio Pakistan | State media (covers ITCN openings) | Media | B | Comms Lead |  |  |  |  | Official-opening coverage
Pamir Times + GB outlets | GB regional media | Media | B | Comms Lead |  |  |  |  | Home-audience pride story
KIU / UoBS leadership | GB universities (KUBIC incubator) | Academia | C | GBSHA Liaison |  |  |  |  | Talent-pipeline narrative
Timeline: DB locked 10 Sep → officeholders verified 10 Sep → letters ready 11 Sep → A-list dispatched 14 Sep (via P@SHA secretariat / ECG protocol / GB Secretary IT) → B-list 16 Sep → RSVPs chased 16–19 Sep → slots confirmed 21 Sep. Every "Visited" row must gain a Follow-up owner the same evening.

## Government-VIP Engagement
GOVERNMENT & VIP ENGAGEMENT — EVERY VISIT PRODUCES AN ASK
A VIP visit without a specific ask is a photo op. Prepare: objective → ask → talking points → host → photo plan → follow-up. Align Day-1 slots with the official opening protocol (via ECG).
1. VIP ENGAGEMENT PLAN (A-list)
VIP / delegation | Objective of the visit | Specific ask | Channel for invite | Invite date | Status | Visit slot | Host / escort | Media plan | Follow-up (what & who)
Federal IT Minister | GB on the national IT map; ministerial endorsement quote | Include GB in national IT-export programs; endorse 3-year pavilion | ECG protocol + P@SHA | 2026-09-14 |  | Day 1 during opening round | PD + Umair Nizam (request) | Photo at ecosystem wall + same-day post + press line | Thank-you letter + program follow-up memo — PD
Secretary MoITT | Policy-level GB inclusion | GB firms in PSEB schemes & subsidy windows | P@SHA secretariat | 2026-09-14 |  | Day 1–2 | PD | Photo + LinkedIn post | Policy one-pager within 7 days — PD
CEO PSEB | Convert diagnostic recommendation into money | Recurring expo-subsidy line for GB firms; GB firms in PSEB intl pavilions (GITEX) | P@SHA intro | 2026-09-14 |  | Day 2 morning | Sponsorship Lead | Photo + post | Subsidy proposal within 7 days — Sponsorship
CEO Ignite | GB startup-support footprint | Incubation/NIC presence or program for GB | P@SHA intro | 2026-09-14 |  | Day 2 | PD | Photo + post | Concept note — PMO
CM GB / GB IT Minister | Home-government ownership of the story | Year-2 co-funding commitment + GB IT policy support | Secretary IT Zameer Abbas | 2026-09-14 |  | Day 1 (if in Karachi) or virtual address | PD + GBSHA | GB media push (Pamir Times etc.) | Co-funding proposal — PD
Umair Nizam (SVC P@SHA / ECG) | Cement patronage; 3-year frame | Written 3-yr confirmation incl. Lahore Jan 2027; stage slot for GB story | Direct | 2026-09-14 |  | Day 1 first hour | PD | Tour video + joint post | Year-2 planning meeting date — PD
Chairman P@SHA | Institutional continuity beyond individuals | P@SHA GB office follow-through; GB seat in committees | P@SHA secretariat | 2026-09-14 |  | Day 2 (MOU ceremony guest) | PD | MOU ceremony photos | Membership drive for GB firms — GBSHA
TDAP IT division | Export-platform access | 2 GB firms in next GITEX delegation; intro to 5 intl delegations at show | ECG | 2026-09-15 |  | Day 2–3 | BD Lead | Post | GITEX application follow-up — BD
VC walk-through (group) | Investor exposure for product companies | 2nd meetings with ≥3 GB companies | BD direct + P@SHA intro | 2026-09-15 |  | Day 2 14:00 group tour | BD Lead | Reel + post | Data-room follow-ups — companies
Diplomatic/intl delegations | International visibility | Market-entry conversations; pavilion stop on official tours | TDAP/ECG protocol | 2026-09-15 |  | Day 3 focus | Stakeholder Lead | Flag-moment photos | Per-delegation notes — Stakeholder
2. PROTOCOL CHECKLIST
Welcome flow: reception spots VIP → alerts host on WhatsApp → host greets at pavilion edge → 60-second ecosystem-wall tour → 2 company pods (rotate fairly across visits) → guestbook + photo moment → souvenir.
Souvenir: small GB handicraft (gemstone/woodwork) with "Made in GB" card — order 20 pieces by 15 Sep (Logistics).
60-second tour script (rehearsed by all hosts): GB = $15–18M sector, 120 active firms, 3–4k freelancers → 10 companies here to do business → the ask.
Guestbook: every VIP signs; photograph the page; transcribe to this sheet same evening.
Photo discipline: one photographer per visit; shots at ecosystem wall (stats visible) + with company founders; captions logged immediately.
Official-opening day: coordinate with ECG protocol office on the ministerial route — request pavilion inclusion by 15 Sep.
Fallback: VIP no-show → host records 60-sec video message invite for them; follow-up meeting requested post-event.

## Pavilion Design & Branding
PAVILION DESIGN & BRANDING — ONE STORY, TEN PROOF POINTS
Identity: "Made in GB" (already in the public narrative via P@SHA). The pavilion reads as ONE ecosystem statement — mountains-to-markets — with 10 equal company pods as proof. Space assumption A2: ≈90 m² (confirm exact dimensions from exhibitor manual by 8 Sep before any production).
1. CONCEPT & NARRATIVE
Core message | Gilgit-Baltistan is Pakistan's emerging technology frontier: $15–18M sector, 100–120 active companies, 3,000–4,000 freelancers, STPs in Gilgit/Skardu/Hunza — and it exports. (Source: P@SHA GB Diagnostic, Nov 2025 — cite on the wall.)
Visual identity | Mountain-horizon motif + clean tech typography; deep green/slate + snow white; "Made in GB" wordmark consistent across fascia, pods, screens, social. No company outshines the collective brand; every pod gets identical prominence.
Message hierarchy | 1) GB is a real tech ecosystem (wall) → 2) These 10 companies are open for business (pods) → 3) Here is how you engage (QR lead form, meeting corner, MOU moments).
Tone | Confident, factual, export-ready. Avoid "remote/underdog" framing; the mountains are a brand asset, not an excuse.
2. ZONE PLAN (for ≈90 m² — re-proportion once dimensions confirmed)
Zone | Purpose / contents | Approx. area | Owner on site | Status | Notes
Reception & info counter | Welcome, visitor registration QR, guestbook, brochures, souvenir stock, rota anchor | 8 m² | Reception rota |  | Front edge, open aspect
10 company pods | Uniform template: logo, one-liner, 3 icons, QR; counter + stool + demo screen/laptop per pod | ~50 m² (5 m² each) | Company reps ×2 |  | Identical footprint — fairness is policy
GB ecosystem wall | Stats infographic, GB tech-geography map, program logos (STPs, e-Rozgaar), QR to ecosystem page; VIP photo backdrop | 8 m² | Host on duty |  | Visible from aisle; sources cited
Meeting corner | 6-pax table + 4-pax high table; 2 concurrent 45-min B2B slots; MOU signings staged here | 10 m² | Meeting desk |  | Semi-screened, not closed
Demo / media wall | Large screen with 3-min loop; reels shot here; interviews corner | 6 m² | Comms Lead
Storage (lockable) | Print stock, equipment cases, personal bags, cash box | 4 m² | Logistics |  | Lockable cabinet ordered via contractor
Circulation | Open flow — no dead-end aisles; wheelchair-passable | ~4 m² | —
3. PRODUCTION CHECKLIST — print in KARACHI; proofs 15 Sep; venue delivery 20 Sep 10:00
Item | Spec / contents | Deadline | Owner | Status | Notes
Main backdrop | "Made in GB — Gilgit-Baltistan Technology Pavilion" + sponsor logos (Title/Gold) | 2026-09-20 | Design Lead |  | Doubles as VIP/MOU photo wall
Fascia strips ×10 + entrance header | Pavilion name + company names per module | 2026-09-20 | Design Lead |  | Per shell-scheme spec (A8)
Company pod graphics ×10 | Uniform template from company assets (2.5) | 2026-09-20 | Design Lead |  | Late assets → template-only pod
Ecosystem wall print | Stats + map + citations | 2026-09-20 | Design Lead
Roll-up standees ×6 | 2 pavilion, 2 program (e-Rozgaar/STP story), 2 sponsor board | 2026-09-20 | Design Lead |  | Reusable for Lahore Jan 2027
QR standees ×12 | Central lead form + per-company profile QRs | 2026-09-20 | BD + Design |  | Test scans before printing
Pavilion booklet ×500 | 20-page: ecosystem story + 1 page per company + contact directory | 2026-09-19 | Comms + Design |  | PDF version for QR download
Company one-pagers ×10×150 | From meeting kits | 2026-09-19 | Companies Lead
Delegate polos ×30 | "Made in GB" branded — uniform look on show days | 2026-09-18 | Logistics |  | Print in GB or Karachi, whichever is faster
Loop video (3 min) + slide loop | Ecosystem intro + 10 company clips + stats | 2026-09-17 | Comms Lead |  | On 2 USBs + cloud + laptop backup
Guestbook + lanyards + badge extras | Reception kit | 2026-09-18 | Logistics
Souvenirs ×20 | GB handicraft + "Made in GB" card | 2026-09-15 | Logistics |  | Carried from GB — pack with care
4. WHAT ECG PROVIDES vs WHAT WE PRODUCE — resolve from exhibitor manual by 8 Sep (Assumption A8)
To confirm with ECG: exact pavilion dimensions & orientation (A2) · open sides · wall type & height · fascia spec · carpet · power points (count/amps) · lighting · furniture included · cleaning · security · wifi quality · rigging rules · contractor rate card · build access times 19–21 Sep · pass allocation (A7).
We produce/rent regardless: all graphics & print, screens (rent via contractor), lead-gen system, booklet, polos, souvenirs, hotspot internet backup.
Rule: nothing goes to print before dimensions and fascia specs are confirmed in writing. Print freeze 12 Sep; error-fix window to 15 Sep proofs only.

## Logistics
LOGISTICS — GILGIT/SKARDU/HUNZA → KARACHI AND BACK, WITH WEATHER MATH
Hard constraint: everyone in Karachi by 20 Sep 18:00. GIL–ISB flies Fri/Sat/Sun only (48-seat ATR, frequent weather cancellations) → the plan uses Fri 18 Sep flights with a same-night road fallback (NATCO ~18h). Skardu contingent has more reliable jet service. All bookings done by 11 Sep.
1. TRAVEL WAVES & FALLBACK RULES
Wave | Who | Route | Depart | Arrive KHI by | Fallback | Owner | Booked? | Cost head | Notes
Advance | 2 pax (Logistics + Design) | Any 17–18 Sep routing | 18-Sep | 19-Sep 12:00 | Already down-country member acts as advance | Logistics Lead |  | Travel | Vendor check, venue access, contractor recon 19 Sep
Main (Gilgit) | ~16 pax | GIL→ISB PIA Fri 18 Sep → ISB→KHI 19 or 20 Sep | 18-Sep | 20-Sep 18:00 | PIA cancels → NATCO road Fri night → ISB Sat → fly KHI Sun 20 Sep | Logistics Lead |  | Travel | Buffer day built in — do NOT book GIL flights for 20 Sep
Skardu/Hunza contingent | ~5 pax | Skardu jets (PIA/Airblue) → ISB/KHI | 18/19-Sep | 20-Sep 18:00 | Road to ISB (12h+) if flights cancel | Logistics Lead |  | Travel | Jet service more weather-reliable than GIL ATR
Down-country members | Any already in ISB/LHE/KHI | Direct to KHI | 19/20-Sep | 20-Sep 18:00 | — | Logistics Lead |  | Travel
Return | All | KHI→ISB 25/26 Sep → GIL Fri 27 Sep or road | 25-Sep | — | Extra hotel night budgeted if GIL flight cancels | Logistics Lead |  | Travel | Materials back-haul per storage plan (9.9)
2. DELEGATE MANIFEST (target 25 = 10×2 reps + 5 core; fill by 9–11 Sep; passes data to ECG 12 Sep)
# | Name | Company / role | CNIC | Phone | Departure city | Wave | Hotel room | Pass issued | Medical / notes (voluntary)
1 | Example: S. Ali (replace) | Karakoram Soft — rep 1 | 71501-xxxxxxx-x | 03xx-xxxxxxx | Gilgit | Main | R-04 (twin) | N
3. ACCOMMODATION, TRANSPORT & VENUE
Hotel: ~13 rooms (twin-share), 19/20 → 25 Sep, walking/short-drive to Expo Centre Karachi (University Rd/Gulshan side). Negotiate group rate + late checkout 25 Sep. Confirm by 12 Sep.
Ground transport: 2 × 14-seat vans with drivers, 20–25 Sep; fixed daily schedule hotel↔venue (08:15 out / 18:45 + 21:00 back); airport transfers per manifest.
Venue: Expo Centre Karachi — setup access 19–21 Sep, show 22–24 Sep 10:00–18:00, dismantle 25 Sep. ECG ops +92-21-38709970; freight agent (only if shipping from GB): APT Showfreight, +92 21 32411158-9.
4. EQUIPMENT & DOCUMENTS CHECKLIST (packed by 17 Sep; owner: Logistics)
Item | Qty | Owner | Packed? | Notes
Laptops + demo devices (per company) | 10+ sets | Companies |  | Each company self-carries; listed in needs survey
Hotspot routers + Jazz/Zong SIMs | 2 + 25 | Logistics |  | SCOM unreliable down-country; buy SIMs on arrival 20 Sep
Extension leads + power strips | 8 | Logistics |  | Venue sockets are scarce
HDMI/USB-C cables, clickers, adapters | 1 kit | Logistics
USBs with loop video + full asset backup | 3 | Comms |  | Plus cloud copies
Paper lead pads + pens (fallback) | 10 pads | BD |  | For internet outages
First-aid kit + basic meds | 1 | Logistics |  | Karachi heat: ORS/hydration reminders
Stationery, tape, cable ties, scissors, markers | 1 box | Logistics |  | Setup-day saviors
Cash float + expense log | PKR 100k | Sponsorship/Finance |  | Receipts mandatory
Delegate packs: schedule, rota, emergency card, pass plan | 25 | Logistics |  | Distributed 20 Sep at hotel
Souvenirs (VIP) + guestbook | 20 + 1 | Stakeholder |  | Carried from GB
CNIC copies + commitment forms + MOU folders | 1 file | PMO |  | Physical + cloud
5. EMERGENCY & CONTINUITY
Emergency card (every delegate): PD phone · Logistics phone · hotel address · van drivers · ECG ops +92-21-38709970 · venue security · nearest hospital: Aga Khan University Hospital · Edhi 115.
Continuity: if any single person is unavailable, their backup (Committee sheet) holds their checklist; workbook + drive give full state. Daily 18:00 update is what makes handover possible.
Weather day-risk on return: if 27 Sep GIL flight cancels, NATCO road or extra ISB night — pre-authorized in budget (contingency line).

## B2B Meetings
B2B MEETINGS — TRAFFIC IS VANITY, MEETINGS ARE SANITY, SIGNED WORK IS REALITY
System: 20-account target list per company (due 12 Sep) + central lists → outreach 12–19 Sep → calendar of 45-min slots (2 concurrent, meeting corner) → meeting log below → every meeting ends with a named next step → leads flow to Lead Tracker. Target: ≥40 booked pre-show, ≥40 held.
1. PROCESS & PREPARATION STANDARD
Target-list template (per company, due 12 Sep): Account · Type (client/partner/investor) · Who to meet · Why us (one line) · Intro path (direct/LinkedIn/P@SHA/ECG) · Ask for the meeting. 20 rows each → 200-account pavilion pool (BD consolidates, de-duplicates, resolves conflicts where two companies chase one account).
Outreach scripts: email + LinkedIn + WhatsApp variants; sent from company founders (not the pavilion account) with pavilion credibility line; P@SHA/ECG intros for A-targets via Liaison. All requests logged below with Status = Requested.
Meeting prep rule: no meeting without the kit — pitch, 1-pager, pricing, 2 case studies, follow-up template. Rehearsed 15–16 Sep.
Slot discipline: 45 min hard stop (10:30–17:15 grid), meeting desk keeps the clock; walk-in buffer slots kept 12:00–13:00 and 16:30 daily; VIP tours override B2B for the hosting company only.
Every meeting closes with: agreed next step + date + owner, logged same evening at the 18:30 sync; counterpart becomes a row in Lead Tracker (qualification Hot/Warm/Cold).
2. MEETING CALENDAR GRID — book by writing company + counterpart into a slot (2 concurrent tables: A = 6-pax, B = high table)
Day | Slot | Table A — GB company | Table A — counterpart | Table B — GB company | Table B — counterpart
Day 1 — Tue 22 Sep | 10:30
11:15
12:00 (walk-in buffer)
13:00
13:45
14:30
15:15
16:00
16:30 (walk-in buffer)
17:15
Day 2 — Wed 23 Sep | 10:30
11:15
12:00 (walk-in buffer)
13:00
13:45
14:30
| 15:15 | RESERVED: MOU ceremony 15:00–16:00
16:00
16:30 (walk-in buffer)
17:15
Day 3 — Thu 24 Sep | 10:30
11:15
12:00 (walk-in buffer)
13:00
13:45
14:30
15:15
16:00
16:30 (walk-in buffer)
17:15
3. MEETING LOG — one row per held/scheduled meeting; feeds Dashboard (Status = "Held") and Lead Tracker
Date | Slot | GB company | Counterpart | Counterpart org | Type | Objective | Status | Outcome / notes | Next step + date | Owner | Lead ID
2026-09-23 | 11:15 | Example: Karakoram Soft | H. Raza | Retail chain (KHI) | Client | Scope e-commerce build | Confirmed |  | Proposal by 30 Sep | A. Khan | EX-1
Counting rule: Dashboard "B2B meetings held" counts rows with Status = Held. The example row uses Status = Confirmed so it never inflates the count — replace it with a real meeting.

## MOU & Partnership Tracker
MOU & PARTNERSHIP TRACKER — AN MOU IS A START LINE, NOT A TROPHY
Pipeline: identify (by 13 Sep) → qualify to 3–5 realistic (by 17 Sep) → drafts + light legal review (by 19 Sep) → signing slots Day 2 15:00 with media & witnesses → record commitments + owner + 30-day action BEFORE leaving Karachi → convert: meeting → opportunity → proposal → contract → revenue. Reviews: 24 Oct / 23 Nov / 23 Dec.
ID | Parties | Type | Purpose / scope (one line) | Status | Signing slot | Owner | Signed date | Key commitments (who does what by when) | 30-day action | Conversion stage | Est. value (PKR) | Notes
M-01 | Example: Karakoram Soft × Lahore agency (replace) | MOU | White-label delivery partnership for overflow projects | Identified | Day 2 15:00 | PD |  | Partner routes 2 scoped projects by 31 Oct; KS staffs 3 devs | Kickoff call by 5 Oct | Meeting | 500000 | Example row — replace
OPERATING RULES
Qualification bar (7.2): a candidate MOU must name (a) a concrete purpose, (b) signatories with authority, (c) at least one dated commitment per side. Otherwise it is a photo, not an MOU — decline politely.
Ceremony protocol: printed 2 copies + folders; P@SHA/official witness invited; photographer briefed; caption + post within 4 hours; commitments transcribed to this sheet the same evening.
Conversion reviews (with 30-60-90 sheet): each MOU either advances a stage or gets a written reason + revival date; two consecutive stalls → mark Dormant (no shame, no zombie MOUs).
Success metric is NOT count of MOUs signed. It is: ≥2 at Proposal+ by day 60, ≥1 at Contract/Revenue by day 90, and a documented pipeline value for the 90-day impact report.

## Social Media & PR Calendar
SOCIAL MEDIA, PR & MEDIA — BEFORE / DURING / AFTER
Platforms: LinkedIn (B2B primary) · Facebook (GB community reach) · Instagram (visual) · X (news/tags) · YouTube (video). Hashtags: #MadeInGB #GBPavilion #ITCNAsia2026 + tag @P@SHA/@ITCN accounts. Owner: Comms Lead; companies amplify same-day via the amplification kit. Cadence: pre = 1+/day from 12 Sep; during = 2+/day + stories; after = results week + stories through 15 Oct.
Date | Phase | Platform | Content type | Topic / asset | Owner | Status | Link / notes
2026-09-06 | Pre | All + press note | Announcement | GB IT community gets its pavilion at 28th ITCN Asia Karachi (22–24 Sep) — "Made in GB" (publish once terms confirmed in writing) | Comms Lead
2026-09-08 | Pre | LinkedIn/FB | Ecosystem story | Why GB tech matters: $15–18M sector, 3–4k freelancers, STPs (cite P@SHA diagnostic) | Comms Lead
2026-09-09 | Pre | LinkedIn/FB | Community | Applications recap + selection process transparency post | Comms Lead
2026-09-10 | Pre | LinkedIn | Stakeholder | Thank-you post: P@SHA & ECG commitment; GBSHA partnership | Comms Lead
2026-09-12 | Pre | All | Company spotlight 1/10 | Selected companies announced + spotlight series starts (1/day) | Comms Lead
2026-09-13 | Pre | All | Spotlight 2/10 | Company spotlight | Comms Lead
2026-09-14 | Pre | All | Spotlight 3/10 | Company spotlight | Comms Lead
2026-09-15 | Pre | All + press | Spotlight 4/10 + press kit | Press release to ≥10 outlets; founder interview offers | Comms Lead
2026-09-16 | Pre | All | Spotlight 5/10 + countdown D-6 | Rehearsal behind-the-scenes | Comms Lead
2026-09-17 | Pre | All | Spotlight 6/10 + countdown D-5 | Founder story #1 (women-led angle) | Comms Lead
2026-09-18 | Pre | All | Spotlight 7/10 + journey | Travel-day content: Gilgit airport / KKH — the journey IS the story | Comms Lead
2026-09-19 | Pre | All | Spotlight 8/10 + countdown D-3 | Advance party in Karachi; venue first look | Comms Lead
2026-09-20 | Pre | All | Spotlight 9/10 + setup | Pavilion build timelapse day 1 | Comms Lead
2026-09-21 | Pre | All + press | Spotlight 10/10 + reveal | Pavilion reveal photo set + "doors open tomorrow"; press reminder | Comms Lead
2026-09-22 | During | All | Live day 1 | Opening, VIP visits (same-day), 3 company reels, stories all day | Comms Lead
2026-09-23 | During | All + press | Live day 2 | B2B energy, investor tour, MOU ceremony posts within 4h, networking dinner | Comms Lead
2026-09-24 | During | All | Live day 3 | International visitors, closing thank-you reel, delegation group photo | Comms Lead
2026-09-25 | After | LinkedIn/FB | Wrap | By-the-numbers first look (leads, meetings, MOUs) + gratitude post | Comms Lead
2026-09-29 | After | All + press | Results release | Official results press release + media follow-ups | Comms Lead
2026-10-02 | After | LinkedIn | Report | Post-event report v1 highlights carousel | Comms Lead
2026-10-06 | After | All | Success story 1/10 | Per-company outcome stories, 2/week through 15 Oct | Comms Lead
2026-10-10 | After | YouTube/All | Wrap video | 3-min pavilion film for year-2 sales + sponsor reports | Comms Lead
2026-10-15 | After | All | Series close | Success story 10/10 + "See you in Lahore, 29–31 Jan 2027" | Comms Lead
PRESS & MEDIA OPERATION
Media target list: ProPakistani (covered GB diagnostic — warmest door) · TechJuice · Business Recorder · Dawn (tech/business desks) · Express Tribune · APP & Radio Pakistan (official-opening coverage) · Pamir Times + GB regional outlets (home-pride angle) · The News. Log every send and response beside this list.
Press assets: release (announcement 15 Sep; results 29 Sep) · fact sheet (ecosystem stats with sources) · founder bios & photos · pavilion photo pack (updated daily during show) · spokesperson: PD (+ one woman founder — media requests skew to founder voices).
Amplification kit to companies & partners: same-day reshare pack (image + suggested caption + hashtags) via WhatsApp; sponsors receive tagged versions per fulfillment plan.
Measurement (feeds KPIs sheet): posts published (this sheet) · earned mentions (log links here) · estimated reach screenshots archived to drive for the report.

## Risk & Issue Register
RISK & ISSUE REGISTER — REVIEWED AT EVERY STANDUP
Score = Likelihood × Impact (H=3, M=2, L=1; computed). Any risk scoring 6+ needs its mitigation IN MOTION, not planned. Blocked items from any sheet land here with an owner and a date.
ID | Risk / issue | Category | Like. | Impact | Score | Mitigation (reduce likelihood) | Contingency (if it happens) | Owner | Status
R1 | Weather cancels GIL–ISB flights 18–19 Sep; delegation stranded | Travel | H | H | 9 | Fri 18 Sep flights (not 20th) + buffer day; Skardu jets for that contingent; monitor forecast from 15 Sep | Same-night NATCO road departure (~18h) → ISB 19 Sep → KHI 20 Sep; roles covered by backups until arrival | Logistics Lead | Open
R2 | Pavilion terms (free space, size, passes) not confirmed in writing in time | Governance | M | H | 6 | Written request 3 Sep; PD escalation call 5 Sep; Umair Nizam office + ECG ops both copied | Fall back to paid 9–18 m² booth block for 4–6 companies (budget line); scale roster accordingly | PASHA/ECG Liaison | Open
R3 | 5-day application window too short → thin or contested selection | Companies | M | M | 4 | Direct outreach to 15 strong candidates in parallel; GBSHA push; published rubric for legitimacy | Extend 48h using reserve buffer in schedule; PD casting vote; regrets get Lahore priority | Companies Lead | Open
R4 | Company drop-out after selection (life events, cost, cold feet) | Companies | M | M | 4 | Commitment forms with cost-share clarity; 2 reserves warm; travel booked centrally | Reserve activated within 24h; pod template means graphics swap in hours | Companies Lead | Open
R5 | Funding gap — sponsorships close below 60% of budget | Funding | M | H | 6 | Wave-1 mission-aligned asks by 7 Sep; in-kind offensive; diaspora patron tier | Cost-share fallback per policy A6 (companies self-fund travel); scope cuts: polos, dinner, video → protected core: print, lead-gen, meeting corner | Sponsorship Lead | Open
R6 | Print/production slip in Karachi (proofs late, vendor overload) | Production | M | H | 6 | Vendor selected 12 Sep with penalty clause + named backup vendor; proofs 15 Sep hard gate; delivery 20 Sep 10:00 | Backup vendor same-day switch; minimum viable set = backdrop + fascia + QR standees (24h job) | Design Lead | Open
R7 | Exhibitor manual arrives late → design guesses wrong (A2/A8) | Governance | M | M | 4 | Manual requested with confirmation 3 Sep; chase 5 Sep; design proceeds on 9 m²-module assumption with flex margins | Adaptive layout absorbs ±20% dimension change; fascia reprint as only hard loss | Design Lead | Open
R8 | Venue internet fails → QR lead capture down | Operations | M | M | 4 | 2 hotspot routers + Jazz/Zong SIMs; offline-capable form; nightly export | Paper lead pads + badge photos; transcribe at 18:30 sync | BD Lead | Open
R9 | VIP no-shows (schedules collapse on opening day) | Stakeholders | M | M | 4 | Slots confirmed via protocol offices 21 Sep; hosts flexible; opening-route inclusion requested | Video-message invite recorded; post-event meeting requested; B-list upgraded to fill tour slots | Stakeholder Lead | Open
R10 | Lead follow-up decay after return (the classic expo failure) | Business | H | H | 9 | Owner + due date assigned to EVERY lead before leaving Karachi (6.9); 30/60/90 reviews calendared; PMO chases weekly | PD intervention: reassign stalled leads at 30-day review; company follow-up SLA in commitment form | PMO / Follow-up | Open
R11 | Association-level politics (P@SHA leadership contest, Aug 2026) complicates sign-offs or continuity | Governance | M | M | 4 | Institutional engagement: write to both P@SHA secretariat AND ECG; all commitments in writing; relationships kept with chairman AND SVC offices | 3-year frame anchored with ECG (organizer) which controls the floor; GB govt patronage as second anchor | PD + Liaison | Open
R12 | Karachi heat/health issues for delegation (altitude-to-heat shift) | Safety | M | L | 2 | Hydration briefing; first-aid kit; AKUH on emergency card; sensible rota with breaks | Backup rota absorbs any person down; nearest hospital 15 min | Logistics Lead | Open
R13 | Security situation affects travel or event schedule | External | L | H | 3 | Monitor advisories from 10 Sep; ECG guidance; flexible tickets where possible | Follow ECG/venue protocol; delegation together at hotel; decisions by PD with P@SHA | PD | Open
R14 | Cost inflation vs placeholder budget (quotes come in high) | Funding | M | M | 4 | Real quotes by 6 Sep (A5); 10% contingency line; group negotiation | Scope ladder per R5 contingency; diaspora patron top-up ask | Sponsorship Lead | Open
R15 | Team burnout in 15-day sprint (small committee, day jobs) | Team | M | M | 4 | Max 2 roles/person; daily standup ≤30 min; weekend blocks protected where possible; backups named | PD redistributes load; scope cuts before people break | PD | Open
R16 | Two companies chase the same account / internal competition sours cohesion | Companies | L | M | 2 | BD de-duplicates target pool 13 Sep; conflicts resolved by earliest-relationship rule | Joint meeting with both companies presented as ecosystem choice | BD Lead | Open
R17 | Sponsor rejection rate high — cold market, short runway | Sponsorship | M | H | 6 | Warm intros first (P@SHA/AKDN/GB govt); 25+ target pipeline vs 8 commitments needed; weighted-pipeline tracking from day 3; specific asks, never "support us" | Diaspora patron drive scales up; cost-share trigger per A6; scope ladder to MVB | Sponsorship Lead | Open
R18 | Government/institutional decision cycles exceed the 15-day window | Sponsorship | H | M | 6 | Ask for LOI now, funds later (post-event acceptable); frame PSEB/GB-govt asks as recurring year 2–3 lines; start UNDP/WB conversations for year 2 explicitly | Bridge spend from cost-share/central budget, reimbursed when grant lands; LOIs still count toward the public funding story | PD | Open
R19 | Funding shortfall — coverage <40% of target at the 15 Sep review | Sponsorship | M | H | 6 | Front-load wave-1 (asks out 5 Sep); first-commitment momentum by 10 Sep; weekly gap math at standup | Activate cost-share (companies bear travel/hotel → central floor ≈2.1–2.3M); MVB scope ladder (cut polos, dinner, video, boosts; protect print, lead-gen, meeting corner, 3-day media) | Steering Committee | Open
R20 | Sponsor demands exceed available benefits (exclusivity, agenda control, competitor blocking) | Sponsorship | M | M | 4 | Benefits matrix is the negotiation boundary; only Title carries naming; PD sign-off required for any exception; no editorial control over GB content at any tier | Politely re-anchor to matrix or downgrade tier; walk away — a bad Title costs more than its cash | PD | Open
R21 | Late confirmations after the 12 Sep print freeze | Sponsorship | H | L | 3 | Logo deadline stated in EVERY proposal from day one; deadline notice to all warm targets 11 Sep | Post-12-Sep tier = screens/social/report benefits only — still sellable through 16 Sep | Sponsorship Lead | Open
R22 | Over-dependence on a single major sponsor (concentration + year-2 renewal risk) | Sponsorship | M | H | 6 | Plan caps any one sponsor ≤35% of total raise; three anchor candidates run in parallel (GB govt / SCO / HBL-class); diversified category spread by design | If one anchor dominates: lock a 2-year MoU with them + rebuild diversification for Lahore Jan 2027 | PD | Open
Escalation: score 6+ and not visibly improving for 2 standups → PD; external blockers → PASHA/ECG Liaison same day. Closed risks keep their row (audit trail for year-2 planning).

## Budget Tracker
BUDGET TRACKER — P3.1 FUNDING REQUIREMENT MATRIX (ALL PKR; UNIT COSTS = PLACEHOLDER ESTIMATES, ASSUMPTION A5)
Three scenarios: MINIMUM VIABLE (credible pavilion, nothing else) · RECOMMENDED (the plan as designed) · ENHANCED (adds GB Night, custom fit-out, investor breakfast, PR support). Replace amber unit costs with real quotes by 6 Sep. Funding route classifies each line: Must-fund (cash) / Sponsorable (cash) / In-kind target / Cost-share candidate / Negotiated free. The RECOMMENDED total is the number the sponsorship drive works against.
1. FUNDING SUMMARY (live — anchors used by Dashboard, KPIs and Sponsors sheets)
| Budget requirement — RECOMMENDED scenario | 5120500 | Scenario totals → | MVB: | 4507250 | Enhanced: | 6592300
| Sponsorship committed (Confirmed + Fulfilled, live from Sponsor Pipeline) | 0
| Company contributions pledged (enter per cost-share policy A6) | 0
| Funding gap (recommended scenario) | 5120500
| Coverage % (committed + contributions vs recommended) | 0%
Cost-share lever (Assumption A6): if companies bear their own reps' travel + hotel, the central must-fund floor drops to ≈ PKR 2.1–2.3M (est.) even in the minimum-viable scenario — this is the primary contingency if sponsorship underperforms (Risk R19).
Category | Item / requirement | Mand./Opt. | Unit | Unit cost (PKR) | Qty MVB | Qty REC | Qty ENH | Total MVB | Total REC | Total ENH | Funding route | Potential source | Owner | Status
Pavilion space | ≈90 m² exhibition space — committed free for 3 years (confirm in writing, A1) | Mandatory | lump | 0 | 1 | 1 | 1 | 0 | 0 | 0 | Negotiated free | ECG / P@SHA commitment | PASHA/ECG Liaison
Travel | Gilgit–Islamabad flights, return (PIA) | Mandatory | pax | 27000 | 16 | 16 | 16 | 432000 | 432000 | 432000 | Cost-share candidate | PIA discount (in-kind ask) / companies / sponsor | Logistics Lead
Travel | Skardu–down-country flights, return | Mandatory | pax | 34000 | 5 | 5 | 5 | 170000 | 170000 | 170000 | Cost-share candidate | Companies / sponsor | Logistics Lead
Travel | NATCO road fallback reserve (weather rule) | Mandatory | pax | 8000 | 16 | 16 | 16 | 128000 | 128000 | 128000 | Must-fund (cash) | Central budget — spent only on cancellation | Logistics Lead
Travel | Islamabad–Karachi flights, return | Mandatory | pax | 42000 | 22 | 22 | 22 | 924000 | 924000 | 924000 | Cost-share candidate | Companies / sponsor | Logistics Lead
Travel | Airport transfers (GIL/ISB/KHI) | Mandatory | lump | 60000 | 1 | 1 | 1 | 60000 | 60000 | 60000 | Must-fund (cash) | Central budget | Logistics Lead
Accommodation | Karachi hotel, twin-share room-nights (ENH: +2 single rooms) | Mandatory | room-night | 17000 | 78 | 78 | 90 | 1326000 | 1326000 | 1530000 | In-kind target | Hospitality partner (Regent Plaza / Mövenpick class) / cost-share | Logistics Lead
Local transport | 14-seat vans with driver & fuel | Mandatory | van-day | 16000 | 12 | 12 | 14 | 192000 | 192000 | 224000 | Sponsorable (cash) | Travel partner / central | Logistics Lead
Branding & print | Main backdrop + fascia set | Mandatory | lump | 160000 | 1 | 1 | 1 | 160000 | 160000 | 160000 | Sponsorable (cash) | Title/Gold sponsor | Design Lead
Branding & print | Company pod graphics | Mandatory | pod | 15000 | 10 | 10 | 10 | 150000 | 150000 | 150000 | Sponsorable (cash) | Gold/Silver sponsors | Design Lead
Branding & print | GB ecosystem wall print | Mandatory | lump | 50000 | 1 | 1 | 1 | 50000 | 50000 | 50000 | Sponsorable (cash) | Gold sponsor / GB IT Dept | Design Lead
Branding & print | Roll-up standees | Optional | pc | 9000 | 4 | 6 | 8 | 36000 | 54000 | 72000 | Sponsorable (cash) | Silver sponsors | Design Lead
Branding & print | QR lead-gen standees | Mandatory | pc | 3000 | 12 | 12 | 12 | 36000 | 36000 | 36000 | Must-fund (cash) | Central budget (lead-gen core) | BD Lead
Branding & print | Pavilion booklet (20pp) | Optional | pc | 180 | 300 | 500 | 800 | 54000 | 90000 | 144000 | Sponsorable (cash) | Silver/Supporting sponsors | Comms Lead
Branding & print | Company one-pagers | Mandatory | pc | 30 | 1000 | 1500 | 2000 | 30000 | 45000 | 60000 | Cost-share candidate | Companies (own collateral) | Companies Lead
Branding & print | Delegate polos ("Made in GB") | Optional | pc | 2500 | 0 | 30 | 35 | 0 | 75000 | 87500 | Sponsorable (cash) | Supporting sponsor | Logistics Lead
Branding & print | VIP souvenirs (GB handicraft) + guestbook | Optional | lump | 60000 | 1 | 1 | 1 | 60000 | 60000 | 60000 | Sponsorable (cash) | GB corporate (Serena / KCBL profile) | Stakeholder Lead
Booth fit-out | Custom fit-out upgrade (lounge, arch element, raised branding) | Optional | lump | 400000 | 0 | 0 | 1 | 0 | 0 | 400000 | Sponsorable (cash) | Title sponsor (enhanced only) | Design Lead
Digital & AV | Screen rental (via ECG contractor) | Mandatory | screen | 15000 | 3 | 6 | 8 | 45000 | 90000 | 120000 | In-kind target | AV vendor / Technology partner | Logistics Lead
Digital & AV | Loop video production (3-min) | Optional | lump | 90000 | 0 | 1 | 1 | 0 | 90000 | 90000 | Sponsorable (cash) | Media/Gold sponsor | Comms Lead
Digital & AV | Daily reels editor (show days) | Optional | day | 30000 | 0 | 0 | 3 | 0 | 0 | 90000 | Sponsorable (cash) | Media partner | Comms Lead
Media | Photographer + videographer | Mandatory | day | 28000 | 3 | 5 | 5 | 84000 | 140000 | 140000 | Sponsorable (cash) | Gold sponsor / central | Comms Lead
Media | Paid social boosts | Optional | campaign | 40000 | 0 | 1 | 2 | 0 | 40000 | 80000 | Sponsorable (cash) | Supporting sponsor | Comms Lead
Media | PR support micro-retainer | Optional | lump | 150000 | 0 | 0 | 1 | 0 | 0 | 150000 | Sponsorable (cash) | Enhanced only | Comms Lead
Events | GB networking dinner, Day 2 (35 pax) | Optional | pax | 4500 | 0 | 35 | 0 | 0 | 157500 | 0 | Sponsorable (cash) | Silver sponsor | Stakeholder Lead
Events | "GB Night" invite-only reception, 60 pax (replaces dinner in ENH) | Optional | lump | 350000 | 0 | 0 | 1 | 0 | 0 | 350000 | Sponsorable (cash) | Title sponsor showcase | Stakeholder Lead
Events | Investor breakfast, Day 2 (15 pax) | Optional | lump | 100000 | 0 | 0 | 1 | 0 | 0 | 100000 | Sponsorable (cash) | VC/investment partner | BD Lead
Operations | SIMs + data for delegation (Jazz/Zong) | Mandatory | pax | 1500 | 25 | 25 | 25 | 37500 | 37500 | 37500 | In-kind target | Telecom partner | Logistics Lead
Operations | Stationery, tape, setup misc | Mandatory | lump | 25000 | 1 | 1 | 1 | 25000 | 25000 | 25000 | Must-fund (cash) | Central budget | Logistics Lead
Operations | First aid + booth refreshments/water | Mandatory | lump | 20000 | 1 | 1 | 1 | 20000 | 20000 | 20000 | Must-fund (cash) | Central budget | Logistics Lead
Operations | Cash float, porterage, tips (hidden cost) | Mandatory | lump | 40000 | 1 | 1 | 1 | 40000 | 40000 | 40000 | Must-fund (cash) | Central budget | Sponsorship/Finance
Operations | Reprint / emergency print reserve (hidden cost) | Mandatory | lump | 30000 | 1 | 1 | 1 | 30000 | 30000 | 30000 | Must-fund (cash) | Central budget | Design Lead
Operations | Extra power / venue service fees if manual requires (hidden cost) | Optional | lump | 25000 | 0 | 1 | 1 | 0 | 25000 | 25000 | Must-fund (cash) | Central budget | Logistics Lead
Operations | Bank/transfer charges + misc fees (hidden cost) | Mandatory | lump | 8000 | 1 | 1 | 1 | 8000 | 8000 | 8000 | Must-fund (cash) | Central budget | Sponsorship/Finance
SUBTOTAL | [7 empty] | 4097500 | 4655000 | 5993000
CONTINGENCY | 10% (weather re-books, reprints, overruns) | [6 empty] | 409750 | 465500 | 599300
GRAND TOTAL | per scenario | [6 empty] | 4507250 | 5120500 | 6592300
Reading the matrix: MANDATORY lines define the minimum-viable scenario — the pavilion cannot run credibly without them. What must be funded in cash = "Must-fund" rows (≈ PKR 0.35M) + whatever cost-share and in-kind asks fail to cover. What can be sponsored = every "Sponsorable" row (branding, media, events — the visible things sponsors like). What can come in-kind = hotel, screens, SIMs, fares, print discount. What is negotiated free = the space itself and ECG extras (passes, hall branding spots, delegate-list access). Two-signature rule (PD + Sponsorship Lead) for any single spend > PKR 100,000; actuals within 48h of spend.

## Lead Tracker
LEAD TRACKER — THE SINGLE MOST IMPORTANT POST-EVENT ASSET
Capture: central QR form + per-company QR + badge photo + paper fallback → exported and merged here at the 18:30 sync each show day. Every lead gets an owner and a first-follow-up date BEFORE the delegation leaves Karachi (activity 6.9). Real leads use IDs L-001, L-002… (grey EX rows are format examples and are excluded from all counts).
Qualification: HOT = need + authority + timeline inside 90 days · WARM = real interest, longer timeline · COLD = contact only. BANT-lite notes: Budget? Authority? Need? Timeline? Dashboard counts: leads = IDs starting "L-"; qualified = Hot + Warm; pipeline value = Σ Est. value of L-rows.
Lead ID | Date | Captured by | Visitor name | Organization | Title | Phone | Email | City / country | Interest (company / service) | Type | Qualification | BANT notes | Assigned to | Follow-up due | Follow-up status | Outcome stage | Est. value (PKR) | Notes
EX-1 | 2026-09-22 | Reception QR | A. Visitor | Retail group (KHI) | Head of Digital | 03xx-xxxxxxx | a@retail.pk | Karachi | Karakoram Soft — e-commerce build | Client | Hot (e.g.) | B:yes A:yes N:yes T:Oct | A. Khan | 2026-09-28 | Scheduled | Meeting | 800000 | Example row — replace
EX-2 | 2026-09-23 | Pod QR | B. Delegate | Trade mission (UAE) | Adviser |  | b@mission.ae | Dubai | Pavilion — outsourcing overview | International | Warm (e.g.) | Exploring vendors | BD Lead | 2026-09-30 | Not started | Contacted | 0 | Example row — replace
EX-3 | 2026-09-23 | Paper pad | C. Student | University | Student |  |  | Karachi | Careers question | Other | Cold (e.g.) | — | Reception | 2026-10-02 | Not started | Contacted | 0 | Example row — replace
Follow-up SLA (in company commitment forms): first contact ≤5 working days; Hot leads ≤48h. "No response ×3" closes the loop honestly — do not delete rows. At the 30-day review every L-row must show an outcome stage.

## 30-60-90 Follow-Up
30 / 60 / 90-DAY FOLLOW-UP — WHERE EXPO VALUE IS ACTUALLY CREATED
Anchor: dismantle 25 Sep 2026 → 30-day = 24 Oct · 60-day = 23 Nov · 90-day = 23 Dec. The PMO/Follow-up Lead runs this machine; the PD chairs the three reviews. Rule: every review produces a one-page scorecard shared with committee, companies, P@SHA and sponsors.
Window | Due | Actions | Owner | Metric / evidence | Status | Notes
48 hours | 2026-09-27 | Thank-you wave: personalized email to every lead (from its owner); VIP letters from PD; sponsor thank-yous with photo pack; group post | PMO + companies | 100% thank-yous sent
7 days | 2026-10-02 | All leads merged, de-duplicated, owners confirmed; first contact on 100% of leads (Hot ≤48h); internal retro held; results press release out; Post-Event Report v1 drafted | PMO / Follow-up | 100% first contact; retro notes filed
7 days | 2026-10-02 | MOU commitments transcribed with owners + 30-day actions; counterpart kickoff calls scheduled | PMO | 100% MOUs have dated next step
14 days | 2026-10-09 | Sponsor fulfillment reports delivered (photos, reach, visits, mentions); renewal conversation opened for Lahore Jan 2027 | Sponsorship Lead | All sponsors reported
30 days | 2026-10-24 | 30-DAY REVIEW: 100% leads contacted & staged; follow-up meetings held ≥20; proposals out ≥10; MOU 30-day actions done; stalled items reassigned; scorecard published | PD + PMO | Scorecard v1; funnel numbers
60 days | 2026-11-23 | 60-DAY REVIEW: pipeline value quantified; ≥2 MOUs at Proposal+; 3 case studies published; sponsor renewals mapped | PD + PMO | Scorecard v2; case studies live
60 days | 2026-11-23 | YEAR-2 DECISION: Lahore 29–31 Jan 2027 — participation, size, improvement list from retro; booking confirmed with ECG by 30 Nov; company selection round 2 announced (waitlist first) | PD | Decision memo + ECG booking
90 days | 2026-12-23 | 90-DAY REVIEW & IMPACT REPORT: contracts/revenue counted; jobs & opportunities logged; media reach totalled; stakeholder debrief held (P@SHA/ECG, GB govt, sponsors); public impact story published | PD | Impact report published
90 days | 2026-12-23 | Year-2 master workbook v1 cloned & updated (stakeholder DB, lead learnings, sponsor history carried forward); Lahore committee confirmed | PMO | Workbook v1 ready
CONVERSION SNAPSHOT (live — also mirrored on Dashboard & KPIs)
Leads captured (L-IDs) |  | 0
Qualified (Hot + Warm) |  | 0
At Meeting stage |  | 1
At Proposal / Negotiation |  | 0
Won |  | 0
Pipeline value (PKR, L-rows) |  | 0
MOUs signed |  | 0
MOUs at Proposal+ (conversion) |  | 0

## KPIs & Impact Measurement
KPIs & IMPACT MEASUREMENT — VISIBILITY → CONNECTIONS → LEADS → PARTNERSHIPS → MOUs → BUSINESS → ECONOMIC IMPACT
Targets are RECOMMENDED for a first Karachi outing (Assumption A9) — ratify at kickoff 3–4 Sep, then freeze. Baseline: first GB delegation (Lahore edition — see A3) attended as visitors; 2026 = first exhibiting pavilion, so most baselines are 0/n.a. Grey Actual cells are live formulas; white ones are entered at reviews.
KPI | Definition | Baseline (2025/26 delegation) | Target 2026 | Actual | Source of truth | Owner | Review
Companies exhibiting | Confirmed companies at the pavilion | n.a. (visited, did not exhibit) | 10 | 0 | Participating Companies | Companies Lead | Weekly
Trained reps on floor | 2 per company, passed rehearsals + lead-capture test | n.a. | 20 |  | Rehearsal scorecards | BD Lead | 17 Sep
Budget coverage | Committed sponsorship + contributions vs budget | n.a. | ≥60% | 0% | Budget Tracker | Sponsorship Lead | Weekly
Sponsors closed | Signed commitments (cash or in-kind letter) | n.a. | ≥5 | 0 | Sponsor Pipeline | Sponsorship Lead | Weekly
Leads captured | Unique L-IDs in Lead Tracker | n.a. | ≥150 | 0 | Lead Tracker | BD Lead | Daily (show)
Qualified leads | Hot + Warm | n.a. | ≥50 | 0 | Lead Tracker | BD Lead | Daily (show)
B2B meetings held | Log rows with Status = Held | n.a. | ≥40 | 0 | B2B Meetings | BD Lead | Daily (show)
Investor conversations | Meetings with Type = Investor held | n.a. | ≥10 | 0 | B2B Meetings | BD Lead | Daily (show)
International connections | Leads/meetings with international counterparts | n.a. | ≥15 | 1 | Lead + B2B | BD Lead | Daily (show)
VIP visits hosted | Gov-VIP rows marked Visited | n.a. | ≥8 | 0 | Gov-VIP Engagement | Stakeholder Lead | Daily (show)
MOUs signed | Signed at/post ITCN | n.a. | ≥5 | 0 | MOU Tracker | PMO | Show + reviews
MOUs converting | At Proposal/Contract/Revenue stage | n.a. | ≥2 by day 60 | 0 | MOU Tracker | PMO | 30/60/90
Proposals out (leads) | L-rows at Proposal+ | n.a. | ≥10 by day 30 | 0 | Lead Tracker | PMO | 30/60/90
Contracts / wins | L-rows Won + MOUs at Contract/Revenue | 0 | ≥3 by day 90 | 0 | Lead + MOU | PD | 90-day
Pipeline value (PKR) | Σ Est. value of L-rows | n.a. | Quantified by day 60 | 0 | Lead Tracker | PMO | 30/60/90
Revenue attributed (PKR) | Closed revenue traceable to pavilion | 0 | Reported day 90 |  | Company declarations | PD | 90-day
Jobs / opportunities created | Hires + internships + freelance contracts attributed | n.a. | Reported day 90 |  | Company declarations | PD | 90-day
Social posts published | Calendar rows Published | n.a. | ≥40 | 0 | Social & PR Calendar | Comms Lead | Weekly
Earned media mentions | Articles/segments naming the pavilion | limited (diagnostic coverage only) | ≥8 |  | Coverage log (Social sheet) | Comms Lead | Weekly
Company satisfaction | Post-event survey, 1–10 | n.a. | avg ≥8; 100% would return |  | Survey (28 Sep) | PMO | 7-day
Year-2 momentum | Waitlist applicants for Lahore Jan 2027 | n.a. | ≥15 |  | Selection round 2 | Companies Lead | 60-day
Open risks (health check) | Risk register rows Open | — | Trend ↓ | 22 | Risk Register | PMO | Daily
Measurement honesty rules: a lead is not a meeting; a meeting is not an MOU; an MOU is not revenue. Report all four levels separately in every scorecard. Attribute revenue only where the company confirms the pavilion originated or materially advanced the deal. Year-over-year: this sheet becomes the baseline column for Lahore Jan 2027.

## Post-Event Report
POST-EVENT REPORT — TEMPLATE & LIVE NUMBERS
Report v1 due 2 Oct (7-day close-out); final impact edition due with the 90-day review (23 Dec). Audiences: committee & companies, P@SHA/ECG, GB government, sponsors, public summary. The by-the-numbers block below fills itself from the trackers.
1. BY THE NUMBERS (live)
Companies exhibited | 0
Leads captured | 0
Qualified leads (Hot+Warm) | 0
B2B meetings held | 0
VIP visits hosted | 0
MOUs signed | 0
Pipeline value (PKR) | 0
Sponsorship raised (PKR) | 0
Social posts published | 0
2. REPORT STRUCTURE — section owners & due dates
Section | Contents | Owner | Due | Status
Executive summary | One page: what the GB Pavilion achieved, in the funnel language (visibility → … → impact); the 3-year arc and the Lahore Jan 2027 decision | PD | 2026-10-02
The pavilion & the companies | 10 company mini-profiles with their individual outcomes (leads, meetings, wins) — every company must be able to point at its page | Companies Lead | 2026-10-02
Business results | Funnel table (leads → qualified → meetings → proposals → wins), pipeline value, MOU list with status and next steps | BD + PMO | 2026-10-02
Stakeholder & VIP engagement | Visit log with photos, asks made, responses; guestbook highlights | Stakeholder Lead | 2026-10-02
Media & visibility | Coverage log with links, post metrics, reach estimates, best content | Comms Lead | 2026-10-02
Financials | Budget vs actuals, sponsorship raised, in-kind value, cost per lead/meeting (honest math) | Sponsorship Lead | 2026-10-02
Lessons learned | Retro output: keep / fix / try for Lahore Jan 2027 — specific, owner-tagged | PMO | 2026-10-02
Recommendations & year-2 plan | Pavilion size, company count, funding model, earlier timeline (Lahore has 4 months of runway — use them) | PD | 2026-11-30
90-day impact edition | Adds: contracts/revenue attributed, jobs created, MOU conversions, updated pipeline; published version for public + sponsors | PD | 2026-12-23
3. SIGN-OFF
Project Director | Name / signature / date
PMO / Follow-up Lead | Name / signature / date
PASHA/ECG Liaison (acknowledgement) | Name / signature / date
GBSHA (acknowledgement) | Name / signature / date